## Oct 2016
|  | Historical Requests pre October 2016 | Chiseldon Parish Council (CPC) Action taken | SBC (Swindon Borough Council) Action taken
Highways | 1 | New Road Parking Bays created near Castle View Road turning | Reported to SBC via ward councillors | Highways dept are investigating this | Likely to be a layby. Housing & Highways working today - no more news 25th Nov. Requires Highways and Planning approval before Housing can proceed. 12th Dec | Chiseldon Parish Council to deal
Highways & Streetsmart | 4 | Damaged road signs by Patriot's Arms | Reported to SBC via ward councillors | SBC are waiting for new sign to be delivered
Highways | 6 | Remove "new" traffic island sign on A346 near New Road turning | Reported to Ward Councillor lagan 101002986102 | They have reported to relevant SBC dept
Highways | 8 | Weight limit sign at Hodson | Reported to Ward councillors | WC's have chased Amelia at SBC on 2nd October
| 16 | Bus Bay Parking at the Landmark Hotel | Reported to SBC via ward councillors | SBC will not paint a bus bay on side of the road where hotel is situated, CPC have requested the exisiting bay we re-painted in yellow to show bus drivers where to stop
StreetSmart | 17 | Outside 45 Draycott Road - pot hole repair | Reported to SBC by ward councillors, lagan 101002982059 | Cllr Shaw has chased with mhotline 12th Dec
Highways | 19 | Patriot's Arms roundabout traffic concerns | CPC reported to Ward Councillors 9th Nov | Ward Councillors have requested a speed survey. Cllr Shaw has suggested locations for speed strips
| 23 | Missing traffic signs in Hodson | Reported to SBC via ward councillorson lagan 101002996997 | The village gate that has fallen over:-There is an order already raised to repair it. | Cllr Shaw advised either on order on or request list 12th Dec
| 24 | Same | Reported to SBC via ward councillorson lagan 101002996997 | The village gate Broome Manor Road side of the village :- I have raised an order to repair it. | Cllr Shaw advised either on order on or request list 12th Dec
Been done? | 26 | Same | Reported to SBC via ward councillorson lagan 101002996997 | The wooden post by the pub car park, is a Rights of Way post and is repaired by the Rights of Way Officer .This is Martin Fry and he was informed of the post when it was first reported. | Cllr Shaw advised either on order on or request list 12th Dec
Been done? | 28 | Corner of Mays Lane and Turnball - Large tree needs cutting back | Ward Councillor reported to SBC | Request submitted for tree to be cut if belongs to SBC
| 32 | Road resurfacing required in Windmill Piece | Reported to SBC via ward councillors | Ward Councillor reported to Highways dept | Photos sent to Cllr Shaw 14th Dec by Clerk
Been done? | 34 | Can't cut grass in public areas of Draycott Foliat due to tenants leaving their property on the grass | Reported to SBC via Parishing team when on site visit | Housing officers at SBC to write to tenants asking them to move items to allow grass cutting to take place

## Nov 2016
2016-11-01
|  | Request | CPC action | Ward Councillor/SBC action
| 1 | Resident requested grass verge at Badbury Bottom be cut | Reported to SBC Highways | Highways believe this should be CPC parishing work - ongoing.
Not a CPC parishing, may be privately owned land. Clerk to investigate further. Ongoing 11th Jan - Clerk trying to establish the land owner
Highways | 2 | Resident reported that vehicles parked dangerously between Turnball and Pats Roundabout | Cllr Sunners reported direct to Ward Cllr Shaw | Cllr Shaw reported to Amelia 2nd Nov. Cllr Shaw has involved Police and both Cllr Shaw and police have photo evidence of this.
| 3 | Resident reported direct to Cllr Shaw about dangerous parking at Station Road, when turning out of side street. | Issue went direct to Cllr Shaw | Cllr Shaw asked Amelia to ask Parking Enforcement to investigate and report back 2nd Nov
Been done? | 4 | Street light at Station Road/New Road junction needs a new bulb | None | Cllr Shaw reported to Amelia 2nd Nov & street lighting dept have been advised
Been done? | 7 | Resident on The Crescent requires a drop kerb for wheelchair access | Reported directly to Cllr Shaw | Cllr Shaw reported to Amelia at SBC Hotline. | Ref 101003031586 10 days lead time. 24th Nov
Urgent | 8 | Concrete blocks moved at the entrance to The Firs | Reported directly to Cllr Shaw by Cllr Sunners | Cllr Shaw advised that travellers had been asked to move on. He will keep us informed. | Update 12th Dec. Police cannot act so SBC going to court. CPC has been asked to write supporting letter
Urgent | 10 | Yellow lines on Hodson Road leading to Turnball need painting all the way to the Pat's roundabout | To be reported back to Ward Councillors after public recess on 14th Nov where residents wish to attend to discuss | Photo evidence provided to Cllr Shaw who will talk to Police and SBC about parking issues causing dangerous road conditions | Cllr Shaw has asked for costs for this 2nd Dec. On Highways list 12th Dec
Urgent | 11 | Turning mirror required when exiting Turnball onto Hodson Road | Reported to Ward Councillors | They have reported to Highways for consideration - have requested photos of difficulty in exiting road. Photo's sent | Cllr Shaw has asked for costs for this 2nd Dec
Urgent | 12 | Yellow lines require painting on Turnball when heading towards Hodson Road | Reported to Ward Councillors | They have reported to Highways for consideration - have requested photos of difficulty in exiting road. Photo's sent | Cllr Shaw has asked for costs for this 2nd Dec. On Highways list 12th Dec
Requires update. Can we do it and re-bill it | 14 | Hedge requires cutting on New Road near Patriots arms | Clerk reported directly to Rob Core | Rob core will arrange this with other works happening in Spring 2017 as temp traffic lights will need to be installed. | Done by SBC on 31st Jan
| 20 | INFO - Improvement of signs for Liddington at Medbourne entrance | Ward Cllr Sumner dealing with this with Liddington PC
Urgent | 28 | Turnball & Slipper Lane, can parking restrictions be added, and wheel wash on building site not always being used | Clerk asked Ward Cllrs to get this actioned | Ward Cllr Shaw reponded: Residents park there and will resist parking ban. Needs a TRO. Will contact planning re HGV's and washer. 25th Nov | Planning enforcement to raise an enforcement case to make sure wheel washing carried out. 7th Dec. Further issues reported to Cllr Shaw on 15th Dec. Photo and further info sent to Cllr Shaw on 11th Jan

## Dec 2016
2016-12-01
|  | Request | Date issue received | CPC action | Date reported to Ward Cllrs | Ward Councillor/SBC action | Date Resolved
Streetsmart | 2 | Path near Calley Arms in Hodson eroded and has unsafe surface |  | Clerk reported to Ward Cllrs |  | Cllr Shaw reported to Members Hotline 8th. Clerk chased with Martin Fry 19th Jan. Martin Fry advised that post has been removed and contractor will be scheduled in to make the ground area safe. 24th Jan
Reported by Cllr Bowles
Highways | 3 | Cllr Shaw has requested a light to illuminate the New Road Build Out sign. | 12th Dec | None | NA
Highways | 4 | Exiting New Road onto A346 - request for filter lane made by Cllr Shaw | 12th Dec | None | NA | Should be on Highways list.
Highways | 5 | 30mph speed limits through Hodson as far as traffic lights over the M4. Requested by Cllr Shaw | 12th Dec | None | Na | With Highways.
Streetsmart | 6 | Cllr Shaw reported to Mhotline 3 sunken drains at junction with Burderop Barns. | 13th Dec | None | NA | Cllr Shaw chased with Mhotline 19th Jan. Pot holes confirmed as filled by Paul Spice on 20th Jan
Highways | 7 | Cllr Shaw requested Highways check Hodson Road from Burderop Barns to edge of Chiseldon as roads are breaking up, esp at verges. | 13th Dec | None | NA | Paul Spice at SBC advised that work will be scheduled to do this. 20th Jan
Enforcement | 9 | Road being blocked at Slipper Lane by developers | 15th Dec | Reported to Cllr Shaw | 15th Dec | Planning dept say this is a police matter. CPC have referred them to condition 5 of their original application. Need photo evidence to send back to SBC planning. Clerk to advise residents. Clerk passed on residents. photo to W.Cllrs on 11th Jan
Photo received from resident on 10th Jan and passed to Cllr Shaw. Cllr Shaw updated Mhotline and Heather Carlisle on 11th Jan asking for action to be taken as condition of planning is being ignored.
Streetsmart | 10 | Road sign from Burderop Barns towards Hodson - 50mph sign is bent | 15th Dec | Reported to Cllr Shaw | 15th Dec | Cllr Shaw reported to Mhotline on 18th Dec
Streetsmart | 11 | As above, the sign warning of the bend in the road is bent. | 15th Dec | Reported to Cllr Shaw | 15th Dec | Cllr Shaw reported to Mhotline on 18th Dec
Streetsmart | 12 | New Road sign opposite the turn into Turnball, damaged | NA | NA | NA | Clle Shaw reported to Mhotline on 18th Dec
Streetsmart & Housing | 15 | Bags of rubbish on A346 where houses from Castle View Road back onto the main road | 22nd Dec | Reported to Cllrs Shaw and Foley | 22nd Dec | Cllr Shaw reported to Mhotline on 22nd Dec
| 16 | Bus shelter on Station Road - seat missing screws and no smoking sign from panel | 21st Dec | Cllr Hill reported to Adshel/Clear Channel for repairs in first 2 weeks of Jan | 21st Dec | Update - will be fixing in next month - 4th Jan. | Cllr reported as DONE 18th Jan
Cllr Hill to tape up damaged seat and contact Adshel again 11th Jan
| 17 | Bus shelter on Station Road - time table perspex cover has been damaged | 21st Dec | Cllr Hill reported to Thamesdown buses to be done in Jan | 21st Dec | Update - will be replacing in the next month - 4th Jan | Cllr reported as DONE 18th Jan
| 18 | Track towards the Washpool off Hodson Road, has large deep potholes. Joint responsibility with estate and SBC | NA | Cllr Shaw reported to Mhotline direct | 22nd Dec | Clle Shaw reported to Mhotline on 22nd Dec

## Jan 2017
2017-01-01
| Request | Date issue received | CPC action | Date reported to Ward Cllrs | Ward Councillor/SBC action | Date Resolved
1 | Clerk reported verge damage in Windmill Piece. Mud on pavements | 6th Jan | Reported to W.Cllrs | 6th Jan | Cllr Shaw reported to Mike Ashe at SBC 6th Jan. Follow up email on 12th to ask warden to visit and letter to be written to residents.
2 | Verge damage at 89/91/93 New Road. Mud on paths and resident fell over | 9th Jan in PC meeting | Cllr Shaw at meeting | 9th Jan | Cllr Shaw reported to Mike Ashe at Rob Anscombe at SBC on 10th Jan. Rob Anscombe has an on-site meeting on 16th Jan so will report back after this.
3 | Cookoo bridge footpath needs leaves and debris clearing. | 11th Jan | Who owns this land?
4 | Footpath from Slipper Lane to Strouds Hill clearing - footpath in bad state of repair - H&S issue | 11th Jan | Clerk to report to Ward Cllrs for SBC to fix
5 | Building work at Marlborough Road - A346. Mud on road and pavements | 11th Jan | NA | NA | Cllr Shaw reported to Mhotline on 11th Jan. Requested inspector on site
6 | Fly tipping on A346 on back of houses, on grass verge. Rubbish bags and old toys | 11th Jan | Cllr Rawlings reported to Cllr Shaw | 11th Jan | Cllr Shaw reported to Mhotline on 11th Jan | Clerk noticed this was cleared on 18th Jan
7 | Hedge on A3446 Badbury side over grown and forcing brown signs to bend over | 26th Jan | Reported to Ward Cllrs to get SBC to fix.
8 | Vehicle activated sign on Plough Hill (A346) not working | 27th Jan | Reported to Ward CLlrs to get SBC to fix | 27th Jan | Cllr Shaw reported to Mhotline 27th Jan | cllr Hill reported this was fixed on 1st Feb
9

## Feb 2017
2017-02-01
| Request | Date issue received | CPC action | Date reported to Ward Cllrs | Ward Councillor/SBC action | Date Resolved
1 | Road sign on New Road build out is bent | 1st Feb | Clerk reported to Cllr Shaw and Foley | 1st Feb | Cllr Foley reported to Mhotline 1.2.17
2 | Pot holes on Station Rd near Landmark hotel | 1st Feb | NA | na | Cllr Shaw reported direct to Mhotline
3 | Pot holes in Mays Lane outside Mays cottage | 2nd Feb | Reported to Cllr Shaw | 2nd Feb | Cllr Shaw reported to Mhotline 2nd Feb
4 | Pot hole approaching Hodson from Broome Manor at the first Hodson sign. | 2nd Feb | na | na | Cllr Foley reported direct to Mhotline 2nd Feb
5 | Water laying in dip at Hodson, H&S issue in freezing weather | 2nd Feb | na | na | Cllr Foley reported direct to Mhotline 2nd Feb
6 | Highways assessmeent of road through Hodson requested due to poor state of road | 2nd feb | na | na | Cllr Foley reported direct to Mhotline 2nd Feb