## Oct 2016
2016-10-01
H&S Impact H,M,L | Village Perception H,M,L | SBC division to deal |  | Historical Requests pre October 2016 | Chiseldon Parish Council (CPC) Action taken | SBC (Swindon Borough Council) Action taken
|  | Highways | 1 | New Road Parking Bays created near Castle View Road turning | Reported to SBC via ward councillors | Highways dept are investigating this | Likely to be a layby. Housing & Highways working today - no more news 25th Nov. Requires Highways and Planning approval before Housing can proceed. 12th Dec | Chiseldon Parish Council to deal
L | L | Highways & Streetsmart | 4 | Damaged road signs by Patriot's Arms | Reported to SBC via ward councillors | SBC are waiting for new sign to be delivered
L | L | Highways | 6 | Remove "new" traffic island sign on A346 near New Road turning | Reported to Ward Councillor lagan 101002986102 | They have reported to relevant SBC dept
|  | Highways | 8 | Weight limit sign at Hodson | Reported to Ward councillors | WC's have chased Amelia at SBC on 2nd October
|  |  | 16 | Bus Bay Parking at the Landmark Hotel | Reported to SBC via ward councillors | SBC will not paint a bus bay on side of the road where hotel is situated, CPC have requested the exisiting bay we re-painted in yellow to show bus drivers where to stop
|  | StreetSmart | 17 | Outside 45 Draycott Road - pot hole repair | Reported to SBC by ward councillors, lagan 101002982059 | Cllr Shaw has chased with mhotline 12th Dec
M | M | Highways | 19 | Patriot's Arms roundabout traffic concerns | CPC reported to Ward Councillors 9th Nov | Ward Councillors have requested a speed survey. Cllr Shaw has suggested locations for speed strips
Safety |  |  | 23 | Missing traffic signs in Hodson | Reported to SBC via ward councillorson lagan 101002996997 | The village gate that has fallen over:-There is an order already raised to repair it. | Cllr Shaw advised either on order on or request list 12th Dec
Safety |  |  | 24 | Same | Reported to SBC via ward councillorson lagan 101002996997 | The village gate Broome Manor Road side of the village :- I have raised an order to repair it. | Cllr Shaw advised either on order on or request list 12th Dec
Safety |  | Been done? | 26 | Same | Reported to SBC via ward councillorson lagan 101002996997 | The wooden post by the pub car park, is a Rights of Way post and is repaired by the Rights of Way Officer .This is Martin Fry and he was informed of the post when it was first reported. | Cllr Shaw advised either on order on or request list 12th Dec
|  | Done. Tree has TPO and owner had dealt with trimming | 28 | Corner of Mays Lane and Turnball - Large tree needs cutting back | Ward Councillor reported to SBC | Request submitted for tree to be cut if belongs to SBC
L | M |  | 32 | Road resurfacing required in Windmill Piece | Reported to SBC via ward councillors | Ward Councillor reported to Highways dept | Photos sent to Cllr Shaw 14th Dec by Clerk
|  | Been done? | 34 | Can't cut grass in public areas of Draycott Foliat due to tenants leaving their property on the grass | Reported to SBC via Parishing team when on site visit | Housing officers at SBC to write to tenants asking them to move items to allow grass cutting to take place

## Nov 2016
2016-11-01
H&S Impact H,M,L | Village Perception H,M,L | SBC division to deal |  | Request | CPC action | Ward Councillor/SBC action
|  |  | 1 | Resident requested grass verge at Badbury Bottom be cut | Reported to SBC Highways | Highways believe this should be CPC parishing work - ongoing.
Not a CPC parishing, may be privately owned land. Clerk to investigate further. Ongoing 11th Jan - Clerk trying to establish the land owner
|  | Highways | 2 | Resident reported that vehicles parked dangerously between Turnball and Pats Roundabout | Cllr Sunners reported direct to Ward Cllr Shaw | Cllr Shaw reported to Amelia 2nd Nov. Cllr Shaw has involved Police and both Cllr Shaw and police have photo evidence of this.
|  |  | 3 | Resident reported direct to Cllr Shaw about dangerous parking at Station Road, when turning out of side street. | Issue went direct to Cllr Shaw | Cllr Shaw asked Amelia to ask Parking Enforcement to investigate and report back 2nd Nov
L | L | Been done? | 4 | Street light at Station Road/New Road junction needs a new bulb | None | Cllr Shaw reported to Amelia 2nd Nov & street lighting dept have been advised
L | L | Been done? | 7 | Resident on The Crescent requires a drop kerb for wheelchair access | Reported directly to Cllr Shaw | Cllr Shaw reported to Amelia at SBC Hotline. | Ref 101003031586 10 days lead time. 24th Nov. Cllr Shaw reported still OS on 4th Feb as Highways have no budget. Passed to housing to see if they can help.
|  | Urgent | 8 | Concrete blocks moved at the entrance to The Firs | Reported directly to Cllr Shaw by Cllr Sunners | Cllr Shaw advised that travellers had been asked to move on. He will keep us informed. | Update 12th Dec. Police cannot act so SBC going to court. CPC has been asked to write supporting letter
|  | Urgent | 10 | Yellow lines on Hodson Road leading to Turnball need painting all the way to the Pat's roundabout | To be reported back to Ward Councillors after public recess on 14th Nov where residents wish to attend to discuss | Photo evidence provided to Cllr Shaw who will talk to Police and SBC about parking issues causing dangerous road conditions | Cllr Shaw has asked for costs for this 2nd Dec. On Highways list 12th Dec
Wait for DYL & possible one way system on Turnball |  | Urgent | 11 | Turning mirror required when exiting Turnball onto Hodson Road | Reported to Ward Councillors | They have reported to Highways for consideration - have requested photos of difficulty in exiting road. Photo's sent | Cllr Shaw has asked for costs for this 2nd Dec
|  | Urgent | 12 | Yellow lines require painting on Turnball when heading towards Hodson Road | Reported to Ward Councillors | They have reported to Highways for consideration - have requested photos of difficulty in exiting road. Photo's sent | Cllr Shaw has asked for costs for this 2nd Dec. On Highways list 12th Dec
|  | Requires update. Can we do it and re-bill it | 14 | Hedge requires cutting on New Road near Patriots arms | Clerk reported directly to Rob Core | Rob core will arrange this with other works happening in Spring 2017 as temp traffic lights will need to be installed. | Done by SBC on 31st Jan
|  |  | 20 | INFO - Improvement of signs for Liddington at Medbourne entrance | Ward Cllr Sumner dealing with this with Liddington PC
|  | Urgent | 28 | Turnball & Slipper Lane, can parking restrictions be added, and wheel wash on building site not always being used | Clerk asked Ward Cllrs to get this actioned | Ward Cllr Shaw reponded: Residents park there and will resist parking ban. Needs a TRO. Will contact planning re HGV's and washer. 25th Nov | Planning enforcement to raise an enforcement case to make sure wheel washing carried out. 7th Dec. Further issues reported to Cllr Shaw on 15th Dec. Photo and further info sent to Cllr Shaw on 11th Jan

## Dec 2016
2016-12-01
H&S Impact H,M,L | Village Perception H,M,L | SBC division to deal |  | Request | Date issue received | CPC action | Date reported to Ward Cllrs | Ward Councillor/SBC action | Date Resolved
Ask Sarah |  | Streetsmart | 2 | Path near Calley Arms in Hodson eroded and has unsafe surface |  | Clerk reported to Ward Cllrs |  | Cllr Shaw reported to Members Hotline 8th. Clerk chased with Martin Fry 19th Jan. Martin Fry advised that post has been removed and contractor will be scheduled in to make the ground area safe. 24th Jan
Reported by Cllr Bowles
|  | Highways | 3 | Cllr Shaw has requested a light to illuminate the New Road Build Out sign. | 12th Dec | None | NA
Transport Dev committee |  | Highways | 4 | Exiting New Road onto A346 - request for filter lane made by Cllr Shaw | 12th Dec | None | NA | Should be on Highways list.
Not requested by CPC |  | Highways | 5 | 30mph speed limits through Hodson as far as traffic lights over the M4. Requested by Cllr Shaw | 12th Dec | None | Na | With Highways.
|  | Streetsmart | 6 | Cllr Shaw reported to Mhotline 3 sunken drains at junction with Burderop Barns. | 13th Dec | None | NA | Cllr Shaw chased with Mhotline 19th Jan. Pot holes confirmed as filled by Paul Spice on 20th Jan
|  | Highways | 7 | Cllr Shaw requested Highways check Hodson Road from Burderop Barns to edge of Chiseldon as roads are breaking up, esp at verges. | 13th Dec | None | NA | Paul Spice at SBC advised that work will be scheduled to do this. 20th Jan
|  | Enforcement | 9 | Road being blocked at Slipper Lane by developers | 15th Dec | Reported to Cllr Shaw | 15th Dec | Planning dept say this is a police matter. CPC have referred them to condition 5 of their original application. Need photo evidence to send back to SBC planning. Clerk to advise residents. Clerk passed on residents. photo to W.Cllrs on 11th Jan
Photo received from resident on 10th Jan and passed to Cllr Shaw. Cllr Shaw updated Mhotline and Heather Carlisle on 11th Jan asking for action to be taken as condition of planning is being ignored.
|  | Streetsmart | 10 | Road sign from Burderop Barns towards Hodson - 50mph sign is bent | 15th Dec | Reported to Cllr Shaw | 15th Dec | Cllr Shaw reported to Mhotline on 18th Dec
|  | Streetsmart | 11 | As above, the sign warning of the bend in the road is bent. | 15th Dec | Reported to Cllr Shaw | 15th Dec | Cllr Shaw reported to Mhotline on 18th Dec
|  | Streetsmart | 12 | New Road sign opposite the turn into Turnball, damaged | NA | NA | NA | Clle Shaw reported to Mhotline on 18th Dec | Fixed March 2017
|  | Streetsmart & Housing | 15 | Bags of rubbish on A346 where houses from Castle View Road back onto the main road | 22nd Dec | Reported to Cllrs Shaw and Foley | 22nd Dec | Cllr Shaw reported to Mhotline on 22nd Dec | Clerk noticed cleared Jan 2017
|  |  | 16 | Bus shelter on Station Road - seat missing screws and no smoking sign from panel | 21st Dec | Cllr Hill reported to Adshel/Clear Channel for repairs in first 2 weeks of Jan | 21st Dec | Update - will be fixing in next month - 4th Jan. | Cllr reported as DONE 18th Jan
Cllr Hill to tape up damaged seat and contact Adshel again 11th Jan
|  |  | 17 | Bus shelter on Station Road - time table perspex cover has been damaged | 21st Dec | Cllr Hill reported to Thamesdown buses to be done in Jan | 21st Dec | Update - will be replacing in the next month - 4th Jan | Cllr reported as DONE 18th Jan
|  |  | 18 | Track towards the Washpool off Hodson Road, has large deep potholes. Joint responsibility with estate and SBC | NA | Cllr Shaw reported to Mhotline direct | 22nd Dec | Clle Shaw reported to Mhotline on 22nd Dec | Cllr Shaw chased with Mhotline 1.3.17

## Jan 2017
2017-01-01
H&S Impact H,M,L | Village Perception H,M,L | SBC division to deal |  | Request | Date issue received | CPC action | Date reported to Ward Cllrs | Ward Councillor/SBC action | Date Resolved
|  |  | 1 | Clerk reported verge damage in Windmill Piece. Mud on pavements | 6th Jan | Reported to W.Cllrs | 6th Jan | Cllr Shaw reported to Mike Ashe at SBC 6th Jan. Follow up email on 12th to ask warden to visit and letter to be written to residents.
|  |  | 2 | Verge damage at 89/91/93 New Road. Mud on paths and resident fell over | 9th Jan in PC meeting | Cllr Shaw at meeting | 9th Jan | Cllr Shaw reported to Mike Ashe at Rob Anscombe at SBC on 10th Jan. Rob Anscombe has an on-site meeting on 16th Jan so will report back after this.
|  |  | 3 | Cookoo bridge footpath needs leaves and debris clearing. | 11th Jan | Who owns this land?
|  |  | 4 | Footpath from Slipper Lane to Strouds Hill clearing - footpath in bad state of repair - H&S issue | 11th Jan | Clerk to report to Ward Cllrs for SBC to fix | 9th Feb | Cllr Shaw reported to Mhotline 9th Feb
|  |  | 5 | Building work at Marlborough Road - A346. Mud on road and pavements | 11th Jan | NA | NA | Cllr Shaw reported to Mhotline on 11th Jan. Requested inspector on site
|  |  | 6 | Fly tipping on A346 on back of houses, on grass verge. Rubbish bags and old toys | 11th Jan | Cllr Rawlings reported to Cllr Shaw | 11th Jan | Cllr Shaw reported to Mhotline on 11th Jan | Clerk noticed this was cleared on 18th Jan
|  |  | 7 | Hedge on A3446 Badbury side over grown and forcing brown signs to bend over | 26th Jan | Reported to Ward Cllrs to get SBC to fix. (CLlr Foley passed to Cllr G Sumner) | 26th Jan
|  |  | 8 | Vehicle activated sign on Plough Hill (A346) not working | 27th Jan | Reported to Ward CLlrs to get SBC to fix | 27th Jan | Cllr Shaw reported to Mhotline 27th Jan | cllr Hill reported this was fixed on 1st Feb

## Feb 2017
2017-02-01
H&S Impact H,M,L | Village Perception H,M,L | SBC division to deal |  | Request | Date issue received | CPC action | Date reported to Ward Cllrs | Ward Councillor/SBC action | Date Resolved
|  |  | 1 | Road sign on New Road build out is bent | 1st Feb | Clerk reported to Cllr Shaw and Foley | 1st Feb | Cllr Foley reported to Mhotline 1.2.17 | SBC fixed 9.2.17
|  |  | 2 | Pot holes on Station Rd near Landmark hotel | 1st Feb | NA | na | Cllr Shaw reported direct to Mhotline
|  |  | 3 | Pot holes in Mays Lane outside Mays cottage | 2nd Feb | Reported to Cllr Shaw | 2nd Feb | Cllr Shaw reported to Mhotline 2nd Feb
|  |  | 4 | Pot hole approaching Hodson from Broome Manor at the first Hodson sign. | 2nd Feb | na | na | Cllr Foley reported direct to Mhotline 2nd Feb
|  |  | 5 | Water laying in dip at Hodson, H&S issue in freezing weather | 2nd Feb | na | na | Cllr Foley reported direct to Mhotline 2nd Feb | Gullies cleared 6th Feb
|  |  | 6 | Highways assessment of road through Hodson requested due to poor state of road | 2nd feb | na | na | Cllr Foley reported direct to Mhotline 2nd Feb
|  |  | 7 | Needle in hedgrow along Butts Road | 7th Feb | Reported to Ward Cllrs | 7th Feb | Cllr Foley reported direct to Mhotline 8th Feb | SBC cleared on the 9th

## March 2017
2017-03-01
H&S Impact H,M,L | Village Perception H,M,L | SBC division to deal |  | Request | Date issue received | CPC action | Date reported to Ward Cllrs | Ward Councillor/SBC action | Date Resolved
H | M | Highways | 1 | There are 4 potholes between the Burderop Junction on the Barbary Castle Road and the turning onto Comet Way. 2 on the lefthand side of the road by the turning into the Burderop Barns conversion and 2, also on the lefthand side of the road further up - 1 about 100mtrs from the turn onto Comet Way and 1 opposite the junction itself. | 1.3.17 | NA | 1.3.17 | Cllr Shaw reported direct to Mhotline
|  |  | 2 | the signage for the entrance to the track down to Washpool off the B4005 Hodson Road on the left as you enter Chiseldon from the Burderop side hasn't been completed.This was promised last Autumn and I first reported it nearly one year ago. | 1.3.17 | NA | 1.3.17 | Cllr Shaw reported direct to Mhotline
|  |  | 3 | Footpaths from Church Street via Washpool to Strouds Hill, in bad state of repairs and muddy | 5.3.17 | NA | 5.3.17 | Cllr Shaw reported direct to Mhotline
|  |  | 4 | Tree on Butts Road overhanging road | 4.3.17 | Cllr Brady reported to Cllr Shaw | 5.3.17 |  | Home owner has cut back branches
(a dead deer was also reported on Hodson Road but was immediately removed)
|  |  | 5 | Nettles need clearing back on Strouds Hill green | 4.3.17 | Cllr Rawlings reported to Ward Cllrs | 4.3.17 |  | CPC are going to deal with this as SBC will not. DONE
|  |  | 6 | Tree on footpath to Rec ground from Hodson Road is blocking the path | 4.3.17 | Cllr Brady reported to Cllr Shaw | 4.3.17 |  | Allbuild removed this
|  |  | 7 | Path from Slipper Lane via Home Close to Strouds Hill in poor state of repair | 9.2.17 | Clerk reported to Ward Cllrs | 9.2.17 | Cllr Shw reported direct to Mhotline
|  |  | 8 | Damaged posts at Strouds Hill carpark | 7.3.17 | Clerk reported to Ward Cllrs | 7.3.17 | Cllr Shaw reported to Mhotline, ref 101003094000 | Fixed
|  |  | 9 | Various potholes in Castle View Road - near no. 87 and at Esso Garage end | 17.3.17 | Clerk reported to Ward Cllrs | 21.3.17 | Cllr Foley reported to Mhotline 21.3.17 | Fixed
|  |  | 10 | Concrete blocks moved outside Firs site | 21.3.17 | Cllr Rawlings reported direct to Ward Cllrs | 21.3.17 | Cllr Foley said they will investigate 21.3.17 | Blocks back in place after a clean up
|  |  | 11 | Damage witnessed to grass at Windmill Piece | 16.3.17 | Clerk sent photos to Ward Cllrs 17.3.17 | 17.3.17 | Cllr Foley passed to Mhotline 101003100816 20.3.17 | Answer from Paul Spice: Drear Cllr Foley I went out and inspected this area today and have taken some more photos to send to housing as well as the photos you provided. As there are a lot of council tenant have asked housing for some help in organise some letters to be sent out to the property's as highways have no powers in place to stop this happening, I can organise the grass to be reinstated Kind regards Paul
|  |  | 12 | Potholes in Badbury | 10.2.17 | Ward Cllr Sumner reported direct to Mhotline | 10.2.17 | Lagan 101003076191 | Potholes filled 17.3.17
|  |  | 13 | Path in Badbury from West Farm to Edgeworth very overgrown | 24.3.17 | Clerk reported to Ward Cllr Sumner | 29.3.17
Check with Jenny? |  |  | 14 | Path down Plough Hill towards M4 is overgrown and muddy | 23.3.17 | W Cllr Shaw reported direct to Mhotline | 23.3.17 | Lagan 101003105284 with 10 day SLA
|  |  | 15 | Slipper Lane - mud on roads and sunken footpath | 9.3.17 | 9.3.17 | 9.3.17 |  | Paul Spice visited site and talked to developer. Streetsmart will enforce a clean up.
Update from Sophia |  |  | 16 | Well Close - parking on verge | 8.3.17 | Cllr Rawlings reported to Cllr Shaw | 8.3.17 | Cllr Shaw reported to PC Best
Reported again on 28th March. Same person, different vehicle.
M | L |  | 17 | Streetlight not working outside 33 Hodson Road | 26.3.17 | Cllr Shaw reported direct to Mhotline | 26.3.17
|  |  | 18 | There are several small potholes on the lefthand side of the road near to the turn off onto Dairy Road. Two potholes are at the bottom of the "dip" where there have been previous repairs. Could Paul check as to whether or not that area and one on the other side of the road midway between the turn off to Hodson & Chiseldon need patching? | 27.3.17 | Cllr Shaw reported direct to Mhotline | 27.3.17
I'm noticing cyclists pull out to avoid them.

## April 2017
2017-04-01
H&S Impact H,M,L | Village Perception H,M,L | SBC division to deal |  | Request | Date issue received | CPC action | Date reported to Ward Cllrs | Ward Councillor/SBC action | Date Resolved | Other info
|  |  | 1 | Fly tipped wood in Washpool stream | 13.4.17 | Reported to Allbuild to remove 16.4.17 | NA | NA |  | Removed
|  |  | 2 | 3 wobble posts to be repaired in Strouds Hill | 18.4.17 | Clerk reported to Ward Cllrs | 18.4.17 | Cllr Shaw reported to Mhotline on 19th |  | SBC have marked posted with yellow paint. 23.4.17
M | M |  | 3 | Street light outside 33 Hodson Road broken again | NA | NA | NA | Cllr Shaw reported to Mhotline on 19th
H | M | Highways | 4 | Repaint white lines at Hodson Road/Brimble Hill junction to be repainted | NA | NA | NA | Cllr Shaw reported to Mhotline 19th
L | L |  | 5 | Bus bays on Landmark and Marlborough Road need repainting | 18.4.17 | Cllr Rawlings reported to Cllr Shaw | 18.4.17
|  |  | 6 | Grass verge between Home Close and Washpool needs cutting | 12.4.17 | NA | 12.4.17 | Cllr Shaw reported to Mhotline 101003118782 | Query from Mhotline as to whether CPC cut this. Clerk sent our map over showing we don’t cut this area. 19th April | SBC confirmed they cut end of April.
|  |  | 7 | Resident asked what was being done to get Thames Water to resinstat the damaged roads at Badbury | 20.4.17 | Passed to Ward Cllr Sumner | 23.4.17 | Cllr Sumner has reported to SBC23.4.17 | Will be contacted once work has finished
|  |  | 8 | Japanese Knotweed reported on road from Draycott Foliat to Og St George. By Draycott road sign. | 24.4.17 | Cllr Rawlings copied Email to Cllr Shaw | 24.4.17 | Cllr Shaw reported to Mhotline | SBC checked and on private land. Does look as its been treated recently as new growth is dying off. 25.4.17
L | L |  | 9 | 6 the Cresent - area where tree removed to be re-tarmaced | NA | NA | 27.4.17 | Cllr Shaw chased Mhotline | Mhotline confirmed area will be re-tarmaced 27.4.17
|  |  | 10 | Glass on Draycott Road T junction to Og St George | 27.4.17 | Clerk reported to AllBuild | 27.4.17 |  | Cleared

## May 2017
2017-05-01
H&S Impact H,M,L | Village Perception H,M,L | SBC division to deal |  | Request | Date issue received | CPC action | Date reported to Ward Cllrs | Ward Councillor/SBC action | Date Resolved | Other info
|  |  | 1 | Oil drum dumped on path near Firs camp | 3.5.17 | Reported to Allbuild 3.5.17 | NA | Allbuild removed it | 4.5.17
L | L | Highways | 2 | New Road sign on grass bank hit by SBC and is now wobbly | 6.5.17 | None | 6.5.17 | Cllr Foley reported direct to Mhotline - 101003132565. They have reviewed the situation and added it to the schedule to be repaired. 9th May
|  |  | 3 | Fly tipping end of Strouds Hill | 8.5.17 | Reported to Allbuild | NA | NA
|  |  | 4 | Fly tipping washpool matress | 8.5.17 | Reported to Allbuild | NA | NA
L | L | Highways | 5 | Grit bin outside patriots arms damaged | 17.5.17 | Reported to Cllr Shaw via Cllr Rawlings | 17.5.17 | Cllr Shaw reporte to Mhotline
M | M | Highways | 6 | There are 4 potholes that need filling & several other smaller ones. | 17.5.17 | None | NA | Cllr Shaw reported to Mhotline
Leaving Chiseldon 1 on the lefthand side about 50mtrs. after the 50mph signs.
On the righthand side about 50 mtrs beyond the turn th Hodson.
Almost on the Burderop Junction two potholes in the centre of the road.
Lastly, several weeks ago a number of areas along this road were marked for patching - just a reminder to say the yellow markings are disappearing.
M | L |  | 7 | Butts Road corner - needs vegetation cutting back | 17.5.17 | None |  | Cllr Shaw reported to Mhotlinr |  | Waiting to see if Highways will do this work.
|  |  | 8 | Fly tipped waste outside rear of 4 Richard Jefferies Gardens | 19.5.17 | Reported to AllBuild | 20.5.17 | Lee to have it cleared
|  |  | 9 | Overgrown hedge and verge outside 4 Tatley Walk | 5.5.17 | Clerk to write hedge letter to home owner
|  |  | 10 | Fly tipping outside house in 4 Tatley Walk | 5.5.17 | Clerk has asked SBC Rachel Ind for advice

## June 17
2017-06-01
H&S Impact H,M,L | Village Perception H,M,L | SBC division to deal |  | Request | Date issue received | CPC action | Date reported to Ward Cllrs | Ward Councillor/SBC action | Date Resolved | Other info
|  |  | 1 | Large potholes on A346 just after motorway roundabout | 9th June | Reported to Ward Cllrs | 9th June | lagan 101003161648 | 12th June
L | L | Highways | 2 | Yellow workmans board left on path at New Road | 7th June | Reported to Ward Cllrs | 8th June | Eric Shaw asked Mhotline to check |  | Eric chased 30th July
M | M | StreetSmart | 3 | Streetlight still not working on High Street No.5 | 7th June | Reported toWard Cllrs | 12th June | 13th June - Cllr Shaw reported to Mhotline | Will be looked at within 48 hours (from 13th June) | Lagan 101003163252
|  |  | 4 | 2 abandonded cars in Windmil piece | 7th June | Reported to Ward Cllrs | 9th June |  |  | See later item in July, 1 car remaining & reported to abandoned vehicles team
|  |  | 5 | Road condition at High Street near shop is bad. | 7th June | Reported to Ward Cllrs | 12th June | Cllr Foley reported to Mhotline 13th June |  | Paul Spice from SBC has been out to check area & marked 2 areas for patching
|  |  | 6 | Fly tipped mattress on way to Ogbourne St George | 6th June | Reported to Albuild | NA |  | 10th June | Allbuild removed
|  |  | 7 | Richard Jefferies Garden - fly tipped gravel & dog poo | 4th June | Reported to Allbuild | NA |  | 10th June | Allbuild removed
|  |  | 8 | Fly tipping at 79 Castle View Road | 10th June | NA | NA | Clerk reported to Allbuild to clear | 14th June | Nothing found when Allbuild visited
|  |  | 9 | Overegrown grass blocking 30nmph and village signs at Hodson, Chiseldon and Draycott Foliat | 12th June | Rported to Ward Cllrs 14th June | 14th June | Cllr Foley has reported this | 15th June | Dealt with by SBC
|  |  | 10 | Branches overgrowing Draycot Foliat bus stop | 8th June | Ward Cllr Shaw reported to Mhotline | NA |  | 8th June | Paul Spice has had the branch cut back
M | L |  | 11 | Trees blocking the sign on Plough Hill | 8th June | Ward Cllr Shaw reported to Mhotline | NA |  | 8th June | Paul Spice will get them cut back when birds stop nesting
|  |  | 12 | Overgrown hedges on footpath between school close and elec substation | 5th June | Reported to Ward Cllrs | 11th June | Cllr Shaw reported to Mhotline` | 15th June | Area has been cleared on council properties and other hedge owners written to to remind them to cut hedges back.
Further report by resident on 22nd June that hedges still overgrown. Have reported back to Ward Cllrs on 23rd. Eric reported back to SBC on 23.6.17
|  |  | 13 | Overgrown Tree in Butts Road cemetery | 6th June | Morgan trees have provided quote - going to Env committee | NA | NA
|  |  |  | Building waste dumped at the rear of a house backing onto the Rec Hall track. | [5 empty] | Land is owned by the residents so cannot be forced to clear it.
|  |  | 14 | Pumphouse Lane Badbury - broken bollard | NA | NA |  | Cllr Sumner reported direct to Mhotline | 19.6.17 | Fixed
|  |  | 15 | Overgrown verge on Pumphouse Lane Badbury | 15th June | NA |  |  |  | Clerk report to Cllr Sumner that not CPC responsibility on parishing maps
|  |  | 16 | Some traffic signs missing in Hodson | 28.6.17 | Reported to Ward Cllrs | 28.6.17 | Cllr Shaw reported to Mhotline | 29.6.17
|  |  | 17 | Waste on forest school washpool | 30.6.17 | Reported to SBC to clear as hazardous waste - needles. 30th |  |  |  | SBC visited and cleared site.
|  |  | 18 | Fly tipped waste on Ridgway Road | 30.6.17 | Clerk reported to Allbuild to clear 30th |  |  |  | Private land so CPC or SBC cannot clear

## July 2017
2017-07-01
H&S Impact H,M,L | Village Perception H,M,L | SBC division to deal |  | Request | Date issue received | CPC action | Date reported to Ward Cllrs | Ward Councillor/SBC action | Date Resolved | Other info
L | L | Highways | 1 | Road sign fallen over on New Road near Well Close | 2.7.17 | Reported to Ward Cllrs | 3.7.17 | Reported to Highways lagan 101003173723 |  | Old post removed and new post on order. 5.7.17
|  | Abandoned vehicle team | 2 | Abandoned vehicle in Windmill Piece | 2.7.17 | Reported to Ward Cllrs | 3.7.17 | Reported to abandoned vehicle team. DAV000006
L | M | CPC | 3 | Canney area grass not cut | 4.7.17 | Reported to Allbuild to check | 5.7.17
|  |  | 4 | Overgrown hedge not cut for resident who pays SBC to do so. The Crescent | 3.7.17 | Reported to Ward Cllrs | 5.7.17 | SBC advised that start date for hedge cutting is 1st July so they will get to this area shortly. | 5.7.17 Resident advised
M | M |  | 5 | There's one area on Hodson Road between the Hodson turn off & Dairy Road (on this side) and one in High Street, Chiseldon which were marked but have yet to be done - the yellow paint marks have virtually disappeared. | 14.7.17 | Cllr Shaw reported to Mhotline
There's a pothole by a drain in Mays Lane which needs repair.
Lastly, could the road by the junction with Mays Lane, Turnball, and High Street be swept? Once again the leaves off the tree on one corner is blocking both the gutter & drains in High Street.
|  |  | 6 | Tree on SBC land on Marl Road overgrown into residents garden | 12.7.17 | Clerk reported to Ward Cllrs | Cllr Shaw asked Mhotline to check this out
|  |  |  | Knotweed reported on exit of Chiseldon going to Og St George. |  | Clerk reported to Ward Cllrs | Cllr Shaw as Mhotline to check | SBC (Rob Core) advised nothing they needed to do as on farmers land.
7
|  |  | 8 | Gully on Hodson road needs clearing as rain water overflowing |  |  | Ward Cllr Shaw reported to Mhotline | Env drainage team cleared this
L | L |  | 9 | High Street sign knocked over | 30.7.17 | Clerk reported to Ward Cllrs | Eric reported to Mhotline 21.7.
|  |  | 10 | machine sweeping of May Lane, Turnball and High Street |  |  | Done 17th July | 101003178410

## August 2017
2017-08-01
H&S Impact H,M,L | Village Perception H,M,L | SBC division to deal |  | Request | Date issue received | CPC action | Date reported to Ward Cllrs | Ward Councillor/SBC action | Date Resolved | Other info
H | H | Highways | 1 | Zebra crossing in New Road the white marking are going fast and need repaint | 6.8.17 | Reported direct to WC's | 6.8.17 | Reporting to Mhotline 7.8.17
L | L | Highways | 2 | Bus bays ( yellow) in the main road A346, are very poor not need repainting both sides of the road, I think we asked over a year ago | 6.8.17 | Reported direct to WC's | 6.8.17 | Reporting to Mhotine 7.8.17
L | L | Highways | 3 | Bus bays on B4005 New Road outside the back of the Esso station and bus stop need repainting | 6.8.17 | Reported direct to WC's | 6.8.17 | Reporting to Mhotline 7.8.17
M | M | Highways | 4 | Road resurfacing at High Street by Spar still not carried out. | 9.8.17 | Ward Cllr reported direct to Mhotline | 9.8.17 | Reported to Mhotline
L | L | Highways | 5 | Resident reported that Carrisbrook Terrace needs resurfacing | 9.8.17 | Clerk reported to Ward Cllrs | 10.8.17
M | L | ? | 6 | Hedges overgrown in Draycott Foliat at Bus stop. |  | Cllr Shaw reported direct to Mhotline | 7.8.17. | Has requested site visit.
L | L | CPC | 7 | Overgrown horse chestnut tree hanging into 11 Home Close | 10.8.17 | Clerk reported to Ward Cllrs | 10.8.17 | Asked Mhotline if CPC can cut back