## Oct 2016
2016-10-01
H&S Impact H,M,L | Village Perception H,M,L | SBC division to deal |  | Historical Requests pre October 2016 | Chiseldon Parish Council (CPC) Action taken | SBC (Swindon Borough Council) Action taken
|  | Highways | 1 | New Road Parking Bays created near Castle View Road turning | Reported to SBC via ward councillors | Highways dept are investigating this | Likely to be a layby. Housing & Highways working today - no more news 25th Nov. Requires Highways and Planning approval before Housing can proceed. 12th Dec | Chiseldon Parish Council to deal
L | L | Highways & Streetsmart | 4 | Damaged road signs by Patriot's Arms | Reported to SBC via ward councillors | SBC are waiting for new sign to be delivered
L | L | Highways | 6 | Remove "new" traffic island sign on A346 near New Road turning | Reported to Ward Councillor lagan 101002986102 | They have reported to relevant SBC dept
|  | Highways | 8 | Weight limit sign at Hodson | Reported to Ward councillors | WC's have chased Amelia at SBC on 2nd October
|  |  | 16 | Bus Bay Parking at the Landmark Hotel | Reported to SBC via ward councillors | SBC will not paint a bus bay on side of the road where hotel is situated, CPC have requested the exisiting bay we re-painted in yellow to show bus drivers where to stop
|  | StreetSmart | 17 | Outside 45 Draycott Road - pot hole repair | Reported to SBC by ward councillors, lagan 101002982059 | Cllr Shaw has chased with mhotline 12th Dec
M | M | Highways | 19 | Patriot's Arms roundabout traffic concerns | CPC reported to Ward Councillors 9th Nov | Ward Councillors have requested a speed survey. Cllr Shaw has suggested locations for speed strips
Safety |  |  | 23 | Missing traffic signs in Hodson | Reported to SBC via ward councillorson lagan 101002996997 | The village gate that has fallen over:-There is an order already raised to repair it. | Cllr Shaw advised either on order on or request list 12th Dec
Safety |  |  | 24 | Same | Reported to SBC via ward councillorson lagan 101002996997 | The village gate Broome Manor Road side of the village :- I have raised an order to repair it. | Cllr Shaw advised either on order on or request list 12th Dec
Safety |  | Been done? | 26 | Same | Reported to SBC via ward councillorson lagan 101002996997 | The wooden post by the pub car park, is a Rights of Way post and is repaired by the Rights of Way Officer .This is Martin Fry and he was informed of the post when it was first reported. | Cllr Shaw advised either on order on or request list 12th Dec
|  | Done. Tree has TPO and owner had dealt with trimming | 28 | Corner of Mays Lane and Turnball - Large tree needs cutting back | Ward Councillor reported to SBC | Request submitted for tree to be cut if belongs to SBC
L | M |  | 32 | Road resurfacing required in Windmill Piece | Reported to SBC via ward councillors | Ward Councillor reported to Highways dept | Photos sent to Cllr Shaw 14th Dec by Clerk
|  | Been done? | 34 | Can't cut grass in public areas of Draycott Foliat due to tenants leaving their property on the grass | Reported to SBC via Parishing team when on site visit | Housing officers at SBC to write to tenants asking them to move items to allow grass cutting to take place

## Nov 2016
2016-11-01
H&S Impact H,M,L | Village Perception H,M,L | SBC division to deal |  | Request | CPC action | Ward Councillor/SBC action
|  |  | 1 | Resident requested grass verge at Badbury Bottom be cut | Reported to SBC Highways | Highways believe this should be CPC parishing work - ongoing.
Not a CPC parishing, may be privately owned land. Clerk to investigate further. Ongoing 11th Jan - Clerk trying to establish the land owner
|  | Highways | 2 | Resident reported that vehicles parked dangerously between Turnball and Pats Roundabout | Cllr Sunners reported direct to Ward Cllr Shaw | Cllr Shaw reported to Amelia 2nd Nov. Cllr Shaw has involved Police and both Cllr Shaw and police have photo evidence of this.
|  |  | 3 | Resident reported direct to Cllr Shaw about dangerous parking at Station Road, when turning out of side street. | Issue went direct to Cllr Shaw | Cllr Shaw asked Amelia to ask Parking Enforcement to investigate and report back 2nd Nov
L | L | Been done? | 4 | Street light at Station Road/New Road junction needs a new bulb | None | Cllr Shaw reported to Amelia 2nd Nov & street lighting dept have been advised
L | L | Been done? | 7 | Resident on The Crescent requires a drop kerb for wheelchair access | Reported directly to Cllr Shaw | Cllr Shaw reported to Amelia at SBC Hotline. | Ref 101003031586 10 days lead time. 24th Nov. Cllr Shaw reported still OS on 4th Feb as Highways have no budget. Passed to housing to see if they can help.
|  | Urgent | 8 | Concrete blocks moved at the entrance to The Firs | Reported directly to Cllr Shaw by Cllr Sunners | Cllr Shaw advised that travellers had been asked to move on. He will keep us informed. | Update 12th Dec. Police cannot act so SBC going to court. CPC has been asked to write supporting letter
|  | Urgent | 10 | Yellow lines on Hodson Road leading to Turnball need painting all the way to the Pat's roundabout | To be reported back to Ward Councillors after public recess on 14th Nov where residents wish to attend to discuss | Photo evidence provided to Cllr Shaw who will talk to Police and SBC about parking issues causing dangerous road conditions | Cllr Shaw has asked for costs for this 2nd Dec. On Highways list 12th Dec
Wait for DYL & possible one way system on Turnball |  | Urgent | 11 | Turning mirror required when exiting Turnball onto Hodson Road | Reported to Ward Councillors | They have reported to Highways for consideration - have requested photos of difficulty in exiting road. Photo's sent | Cllr Shaw has asked for costs for this 2nd Dec
|  | Urgent | 12 | Yellow lines require painting on Turnball when heading towards Hodson Road | Reported to Ward Councillors | They have reported to Highways for consideration - have requested photos of difficulty in exiting road. Photo's sent | Cllr Shaw has asked for costs for this 2nd Dec. On Highways list 12th Dec
|  | Requires update. Can we do it and re-bill it | 14 | Hedge requires cutting on New Road near Patriots arms | Clerk reported directly to Rob Core | Rob core will arrange this with other works happening in Spring 2017 as temp traffic lights will need to be installed. | Done by SBC on 31st Jan
|  |  | 20 | INFO - Improvement of signs for Liddington at Medbourne entrance | Ward Cllr Sumner dealing with this with Liddington PC
|  | Urgent | 28 | Turnball & Slipper Lane, can parking restrictions be added, and wheel wash on building site not always being used | Clerk asked Ward Cllrs to get this actioned | Ward Cllr Shaw reponded: Residents park there and will resist parking ban. Needs a TRO. Will contact planning re HGV's and washer. 25th Nov | Planning enforcement to raise an enforcement case to make sure wheel washing carried out. 7th Dec. Further issues reported to Cllr Shaw on 15th Dec. Photo and further info sent to Cllr Shaw on 11th Jan

## Dec 2016
2016-12-01
H&S Impact H,M,L | Village Perception H,M,L | SBC division to deal |  | Request | Date issue received | CPC action | Date reported to Ward Cllrs | Ward Councillor/SBC action | Date Resolved
Ask Sarah |  | Streetsmart | 2 | Path near Calley Arms in Hodson eroded and has unsafe surface |  | Clerk reported to Ward Cllrs |  | Cllr Shaw reported to Members Hotline 8th. Clerk chased with Martin Fry 19th Jan. Martin Fry advised that post has been removed and contractor will be scheduled in to make the ground area safe. 24th Jan
Reported by Cllr Bowles
|  | Highways | 3 | Cllr Shaw has requested a light to illuminate the New Road Build Out sign. | 12th Dec | None | NA
Transport Dev committee |  | Highways | 4 | Exiting New Road onto A346 - request for filter lane made by Cllr Shaw | 12th Dec | None | NA | Should be on Highways list.
Not requested by CPC |  | Highways | 5 | 30mph speed limits through Hodson as far as traffic lights over the M4. Requested by Cllr Shaw | 12th Dec | None | Na | With Highways.
|  | Streetsmart | 6 | Cllr Shaw reported to Mhotline 3 sunken drains at junction with Burderop Barns. | 13th Dec | None | NA | Cllr Shaw chased with Mhotline 19th Jan. Pot holes confirmed as filled by Paul Spice on 20th Jan
|  | Highways | 7 | Cllr Shaw requested Highways check Hodson Road from Burderop Barns to edge of Chiseldon as roads are breaking up, esp at verges. | 13th Dec | None | NA | Paul Spice at SBC advised that work will be scheduled to do this. 20th Jan
|  | Enforcement | 9 | Road being blocked at Slipper Lane by developers | 15th Dec | Reported to Cllr Shaw | 15th Dec | Planning dept say this is a police matter. CPC have referred them to condition 5 of their original application. Need photo evidence to send back to SBC planning. Clerk to advise residents. Clerk passed on residents. photo to W.Cllrs on 11th Jan
Photo received from resident on 10th Jan and passed to Cllr Shaw. Cllr Shaw updated Mhotline and Heather Carlisle on 11th Jan asking for action to be taken as condition of planning is being ignored.
|  | Streetsmart | 10 | Road sign from Burderop Barns towards Hodson - 50mph sign is bent | 15th Dec | Reported to Cllr Shaw | 15th Dec | Cllr Shaw reported to Mhotline on 18th Dec
|  | Streetsmart | 11 | As above, the sign warning of the bend in the road is bent. | 15th Dec | Reported to Cllr Shaw | 15th Dec | Cllr Shaw reported to Mhotline on 18th Dec
|  | Streetsmart | 12 | New Road sign opposite the turn into Turnball, damaged | NA | NA | NA | Clle Shaw reported to Mhotline on 18th Dec | Fixed March 2017
|  | Streetsmart & Housing | 15 | Bags of rubbish on A346 where houses from Castle View Road back onto the main road | 22nd Dec | Reported to Cllrs Shaw and Foley | 22nd Dec | Cllr Shaw reported to Mhotline on 22nd Dec | Clerk noticed cleared Jan 2017
|  |  | 16 | Bus shelter on Station Road - seat missing screws and no smoking sign from panel | 21st Dec | Cllr Hill reported to Adshel/Clear Channel for repairs in first 2 weeks of Jan | 21st Dec | Update - will be fixing in next month - 4th Jan. | Cllr reported as DONE 18th Jan
Cllr Hill to tape up damaged seat and contact Adshel again 11th Jan
|  |  | 17 | Bus shelter on Station Road - time table perspex cover has been damaged | 21st Dec | Cllr Hill reported to Thamesdown buses to be done in Jan | 21st Dec | Update - will be replacing in the next month - 4th Jan | Cllr reported as DONE 18th Jan
|  |  | 18 | Track towards the Washpool off Hodson Road, has large deep potholes. Joint responsibility with estate and SBC | NA | Cllr Shaw reported to Mhotline direct | 22nd Dec | Clle Shaw reported to Mhotline on 22nd Dec | Cllr Shaw chased with Mhotline 1.3.17

## Jan 2017
2017-01-01
H&S Impact H,M,L | Village Perception H,M,L | SBC division to deal |  | Request | Date issue received | CPC action | Date reported to Ward Cllrs | Ward Councillor/SBC action | Date Resolved
|  |  | 1 | Clerk reported verge damage in Windmill Piece. Mud on pavements | 6th Jan | Reported to W.Cllrs | 6th Jan | Cllr Shaw reported to Mike Ashe at SBC 6th Jan. Follow up email on 12th to ask warden to visit and letter to be written to residents.
|  |  | 2 | Verge damage at 89/91/93 New Road. Mud on paths and resident fell over | 9th Jan in PC meeting | Cllr Shaw at meeting | 9th Jan | Cllr Shaw reported to Mike Ashe at Rob Anscombe at SBC on 10th Jan. Rob Anscombe has an on-site meeting on 16th Jan so will report back after this.
|  |  | 3 | Cookoo bridge footpath needs leaves and debris clearing. | 11th Jan | Who owns this land?
|  |  | 4 | Footpath from Slipper Lane to Strouds Hill clearing - footpath in bad state of repair - H&S issue | 11th Jan | Clerk to report to Ward Cllrs for SBC to fix | 9th Feb | Cllr Shaw reported to Mhotline 9th Feb
|  |  | 5 | Building work at Marlborough Road - A346. Mud on road and pavements | 11th Jan | NA | NA | Cllr Shaw reported to Mhotline on 11th Jan. Requested inspector on site
|  |  | 6 | Fly tipping on A346 on back of houses, on grass verge. Rubbish bags and old toys | 11th Jan | Cllr Rawlings reported to Cllr Shaw | 11th Jan | Cllr Shaw reported to Mhotline on 11th Jan | Clerk noticed this was cleared on 18th Jan
|  |  | 7 | Hedge on A3446 Badbury side over grown and forcing brown signs to bend over | 26th Jan | Reported to Ward Cllrs to get SBC to fix. (CLlr Foley passed to Cllr G Sumner) | 26th Jan
|  |  | 8 | Vehicle activated sign on Plough Hill (A346) not working | 27th Jan | Reported to Ward CLlrs to get SBC to fix | 27th Jan | Cllr Shaw reported to Mhotline 27th Jan | cllr Hill reported this was fixed on 1st Feb

## Feb 2017
2017-02-01
H&S Impact H,M,L | Village Perception H,M,L | SBC division to deal |  | Request | Date issue received | CPC action | Date reported to Ward Cllrs | Ward Councillor/SBC action | Date Resolved
|  |  | 1 | Road sign on New Road build out is bent | 1st Feb | Clerk reported to Cllr Shaw and Foley | 1st Feb | Cllr Foley reported to Mhotline 1.2.17 | SBC fixed 9.2.17
|  |  | 2 | Pot holes on Station Rd near Landmark hotel | 1st Feb | NA | na | Cllr Shaw reported direct to Mhotline
|  |  | 3 | Pot holes in Mays Lane outside Mays cottage | 2nd Feb | Reported to Cllr Shaw | 2nd Feb | Cllr Shaw reported to Mhotline 2nd Feb
|  |  | 4 | Pot hole approaching Hodson from Broome Manor at the first Hodson sign. | 2nd Feb | na | na | Cllr Foley reported direct to Mhotline 2nd Feb
|  |  | 5 | Water laying in dip at Hodson, H&S issue in freezing weather | 2nd Feb | na | na | Cllr Foley reported direct to Mhotline 2nd Feb | Gullies cleared 6th Feb
|  |  | 6 | Highways assessment of road through Hodson requested due to poor state of road | 2nd feb | na | na | Cllr Foley reported direct to Mhotline 2nd Feb
|  |  | 7 | Needle in hedgrow along Butts Road | 7th Feb | Reported to Ward Cllrs | 7th Feb | Cllr Foley reported direct to Mhotline 8th Feb | SBC cleared on the 9th

## March 2017
2017-03-01
H&S Impact H,M,L | Village Perception H,M,L | SBC division to deal |  | Request | Date issue received | CPC action | Date reported to Ward Cllrs | Ward Councillor/SBC action | Date Resolved
H | M | Highways | 1 | There are 4 potholes between the Burderop Junction on the Barbary Castle Road and the turning onto Comet Way. 2 on the lefthand side of the road by the turning into the Burderop Barns conversion and 2, also on the lefthand side of the road further up - 1 about 100mtrs from the turn onto Comet Way and 1 opposite the junction itself. | 1.3.17 | NA | 1.3.17 | Cllr Shaw reported direct to Mhotline
|  |  | 2 | the signage for the entrance to the track down to Washpool off the B4005 Hodson Road on the left as you enter Chiseldon from the Burderop side hasn't been completed.This was promised last Autumn and I first reported it nearly one year ago. | 1.3.17 | NA | 1.3.17 | Cllr Shaw reported direct to Mhotline
|  |  | 3 | Footpaths from Church Street via Washpool to Strouds Hill, in bad state of repairs and muddy | 5.3.17 | NA | 5.3.17 | Cllr Shaw reported direct to Mhotline
|  |  | 4 | Tree on Butts Road overhanging road | 4.3.17 | Cllr Brady reported to Cllr Shaw | 5.3.17 |  | Home owner has cut back branches
(a dead deer was also reported on Hodson Road but was immediately removed)
|  |  | 5 | Nettles need clearing back on Strouds Hill green | 4.3.17 | Cllr Rawlings reported to Ward Cllrs | 4.3.17 |  | CPC are going to deal with this as SBC will not. DONE
|  |  | 6 | Tree on footpath to Rec ground from Hodson Road is blocking the path | 4.3.17 | Cllr Brady reported to Cllr Shaw | 4.3.17 |  | Allbuild removed this
|  |  | 7 | Path from Slipper Lane via Home Close to Strouds Hill in poor state of repair | 9.2.17 | Clerk reported to Ward Cllrs | 9.2.17 | Cllr Shw reported direct to Mhotline
|  |  | 8 | Damaged posts at Strouds Hill carpark | 7.3.17 | Clerk reported to Ward Cllrs | 7.3.17 | Cllr Shaw reported to Mhotline, ref 101003094000 | Fixed
|  |  | 9 | Various potholes in Castle View Road - near no. 87 and at Esso Garage end | 17.3.17 | Clerk reported to Ward Cllrs | 21.3.17 | Cllr Foley reported to Mhotline 21.3.17 | Fixed
|  |  | 10 | Concrete blocks moved outside Firs site | 21.3.17 | Cllr Rawlings reported direct to Ward Cllrs | 21.3.17 | Cllr Foley said they will investigate 21.3.17 | Blocks back in place after a clean up
|  |  | 11 | Damage witnessed to grass at Windmill Piece | 16.3.17 | Clerk sent photos to Ward Cllrs 17.3.17 | 17.3.17 | Cllr Foley passed to Mhotline 101003100816 20.3.17 | Answer from Paul Spice: Drear Cllr Foley I went out and inspected this area today and have taken some more photos to send to housing as well as the photos you provided. As there are a lot of council tenant have asked housing for some help in organise some letters to be sent out to the property's as highways have no powers in place to stop this happening, I can organise the grass to be reinstated Kind regards Paul
|  |  | 12 | Potholes in Badbury | 10.2.17 | Ward Cllr Sumner reported direct to Mhotline | 10.2.17 | Lagan 101003076191 | Potholes filled 17.3.17
|  |  | 13 | Path in Badbury from West Farm to Edgeworth very overgrown | 24.3.17 | Clerk reported to Ward Cllr Sumner | 29.3.17
Check with Jenny? |  |  | 14 | Path down Plough Hill towards M4 is overgrown and muddy | 23.3.17 | W Cllr Shaw reported direct to Mhotline | 23.3.17 | Lagan 101003105284 with 10 day SLA
|  |  | 15 | Slipper Lane - mud on roads and sunken footpath | 9.3.17 | 9.3.17 | 9.3.17 |  | Paul Spice visited site and talked to developer. Streetsmart will enforce a clean up.
Update from Sophia |  |  | 16 | Well Close - parking on verge | 8.3.17 | Cllr Rawlings reported to Cllr Shaw | 8.3.17 | Cllr Shaw reported to PC Best
Reported again on 28th March. Same person, different vehicle.
M | L |  | 17 | Streetlight not working outside 33 Hodson Road | 26.3.17 | Cllr Shaw reported direct to Mhotline | 26.3.17
|  |  | 18 | There are several small potholes on the lefthand side of the road near to the turn off onto Dairy Road. Two potholes are at the bottom of the "dip" where there have been previous repairs. Could Paul check as to whether or not that area and one on the other side of the road midway between the turn off to Hodson & Chiseldon need patching? | 27.3.17 | Cllr Shaw reported direct to Mhotline | 27.3.17
I'm noticing cyclists pull out to avoid them.

## April 2017
2017-04-01
H&S Impact H,M,L | Village Perception H,M,L | SBC division to deal |  | Request | Date issue received | CPC action | Date reported to Ward Cllrs | Ward Councillor/SBC action | Date Resolved | Other info
|  |  | 1 | Fly tipped wood in Washpool stream | 13.4.17 | Reported to Allbuild to remove 16.4.17 | NA | NA |  | Removed
|  |  | 2 | 3 wobble posts to be repaired in Strouds Hill | 18.4.17 | Clerk reported to Ward Cllrs | 18.4.17 | Cllr Shaw reported to Mhotline on 19th |  | SBC have marked posted with yellow paint. 23.4.17
M | M |  | 3 | Street light outside 33 Hodson Road broken again | NA | NA | NA | Cllr Shaw reported to Mhotline on 19th
H | M | Highways | 4 | Repaint white lines at Hodson Road/Brimble Hill junction to be repainted | NA | NA | NA | Cllr Shaw reported to Mhotline 19th
L | L |  | 5 | Bus bays on Landmark and Marlborough Road need repainting | 18.4.17 | Cllr Rawlings reported to Cllr Shaw | 18.4.17
|  |  | 6 | Grass verge between Home Close and Washpool needs cutting | 12.4.17 | NA | 12.4.17 | Cllr Shaw reported to Mhotline 101003118782 | Query from Mhotline as to whether CPC cut this. Clerk sent our map over showing we don’t cut this area. 19th April | SBC confirmed they cut end of April.
|  |  | 7 | Resident asked what was being done to get Thames Water to resinstat the damaged roads at Badbury | 20.4.17 | Passed to Ward Cllr Sumner | 23.4.17 | Cllr Sumner has reported to SBC23.4.17 | Will be contacted once work has finished
|  |  | 8 | Japanese Knotweed reported on road from Draycott Foliat to Og St George. By Draycott road sign. | 24.4.17 | Cllr Rawlings copied Email to Cllr Shaw | 24.4.17 | Cllr Shaw reported to Mhotline | SBC checked and on private land. Does look as its been treated recently as new growth is dying off. 25.4.17
L | L |  | 9 | 6 the Cresent - area where tree removed to be re-tarmaced | NA | NA | 27.4.17 | Cllr Shaw chased Mhotline | Mhotline confirmed area will be re-tarmaced 27.4.17
|  |  | 10 | Glass on Draycott Road T junction to Og St George | 27.4.17 | Clerk reported to AllBuild | 27.4.17 |  | Cleared

## May 2017
2017-05-01
H&S Impact H,M,L | Village Perception H,M,L | SBC division to deal |  | Request | Date issue received | CPC action | Date reported to Ward Cllrs | Ward Councillor/SBC action | Date Resolved | Other info
|  |  | 1 | Oil drum dumped on path near Firs camp | 3.5.17 | Reported to Allbuild 3.5.17 | NA | Allbuild removed it | 4.5.17
L | L | Highways | 2 | New Road sign on grass bank hit by SBC and is now wobbly | 6.5.17 | None | 6.5.17 | Cllr Foley reported direct to Mhotline - 101003132565. They have reviewed the situation and added it to the schedule to be repaired. 9th May
|  |  | 3 | Fly tipping end of Strouds Hill | 8.5.17 | Reported to Allbuild | NA | NA
|  |  | 4 | Fly tipping washpool matress | 8.5.17 | Reported to Allbuild | NA | NA
L | L | Highways | 5 | Grit bin outside patriots arms damaged | 17.5.17 | Reported to Cllr Shaw via Cllr Rawlings | 17.5.17 | Cllr Shaw reporte to Mhotline
M | M | Highways | 6 | There are 4 potholes that need filling & several other smaller ones. | 17.5.17 | None | NA | Cllr Shaw reported to Mhotline
Leaving Chiseldon 1 on the lefthand side about 50mtrs. after the 50mph signs.
On the righthand side about 50 mtrs beyond the turn th Hodson.
Almost on the Burderop Junction two potholes in the centre of the road.
Lastly, several weeks ago a number of areas along this road were marked for patching - just a reminder to say the yellow markings are disappearing.
M | L |  | 7 | Butts Road corner - needs vegetation cutting back | 17.5.17 | None |  | Cllr Shaw reported to Mhotlinr |  | Waiting to see if Highways will do this work. Residents and CPC to do this Nov 2017
|  |  | 8 | Fly tipped waste outside rear of 4 Richard Jefferies Gardens | 19.5.17 | Reported to AllBuild | 20.5.17 | Lee to have it cleared
|  |  | 9 | Overgrown hedge and verge outside 4 Tatley Walk | 5.5.17 | Clerk to write hedge letter to home owner
|  |  | 10 | Fly tipping outside house in 4 Tatley Walk | 5.5.17 | Clerk has asked SBC Rachel Ind for advice

## June 17
2017-06-01
H&S Impact H,M,L | Village Perception H,M,L | SBC division to deal |  | Request | Date issue received | CPC action | Date reported to Ward Cllrs | Ward Councillor/SBC action | Date Resolved | Other info
|  |  | 1 | Large potholes on A346 just after motorway roundabout | 9th June | Reported to Ward Cllrs | 9th June | lagan 101003161648 | 12th June
L | L | Highways | 2 | Yellow workmans board left on path at New Road | 7th June | Reported to Ward Cllrs | 8th June | Eric Shaw asked Mhotline to check |  | Eric chased 30th July
M | M | StreetSmart | 3 | Streetlight still not working on High Street No.5 | 7th June | Reported toWard Cllrs | 12th June | 13th June - Cllr Shaw reported to Mhotline | Will be looked at within 48 hours (from 13th June) | Lagan 101003163252
|  |  | 4 | 2 abandonded cars in Windmil piece | 7th June | Reported to Ward Cllrs | 9th June |  |  | See later item in July, 1 car remaining & reported to abandoned vehicles team
|  |  | 5 | Road condition at High Street near shop is bad. | 7th June | Reported to Ward Cllrs | 12th June | Cllr Foley reported to Mhotline 13th June |  | Paul Spice from SBC has been out to check area & marked 2 areas for patching
|  |  | 6 | Fly tipped mattress on way to Ogbourne St George | 6th June | Reported to Albuild | NA |  | 10th June | Allbuild removed
|  |  | 7 | Richard Jefferies Garden - fly tipped gravel & dog poo | 4th June | Reported to Allbuild | NA |  | 10th June | Allbuild removed
|  |  | 8 | Fly tipping at 79 Castle View Road | 10th June | NA | NA | Clerk reported to Allbuild to clear | 14th June | Nothing found when Allbuild visited
|  |  | 9 | Overegrown grass blocking 30nmph and village signs at Hodson, Chiseldon and Draycott Foliat | 12th June | Rported to Ward Cllrs 14th June | 14th June | Cllr Foley has reported this | 15th June | Dealt with by SBC
|  |  | 10 | Branches overgrowing Draycot Foliat bus stop | 8th June | Ward Cllr Shaw reported to Mhotline | NA |  | 8th June | Paul Spice has had the branch cut back
M | L |  | 11 | Trees blocking the sign on Plough Hill | 8th June | Ward Cllr Shaw reported to Mhotline | NA |  | 8th June | Paul Spice will get them cut back when birds stop nesting | Chased Aug 2018! | hased via EGPA meeting Feb 2019!!
|  |  | 12 | Overgrown hedges on footpath between school close and elec substation | 5th June | Reported to Ward Cllrs | 11th June | Cllr Shaw reported to Mhotline` | 15th June | Area has been cleared on council properties and other hedge owners written to to remind them to cut hedges back.
Further report by resident on 22nd June that hedges still overgrown. Have reported back to Ward Cllrs on 23rd. Eric reported back to SBC on 23.6.17
|  |  | 13 | Overgrown Tree in Butts Road cemetery | 6th June | Morgan trees have provided quote - going to Env committee | NA | NA
|  |  |  | Building waste dumped at the rear of a house backing onto the Rec Hall track. | [5 empty] | Land is owned by the residents so cannot be forced to clear it.
|  |  | 14 | Pumphouse Lane Badbury - broken bollard | NA | NA |  | Cllr Sumner reported direct to Mhotline | 19.6.17 | Fixed
|  |  | 15 | Overgrown verge on Pumphouse Lane Badbury | 15th June | NA |  |  |  | Clerk report to Cllr Sumner that not CPC responsibility on parishing maps
|  |  | 16 | Some traffic signs missing in Hodson | 28.6.17 | Reported to Ward Cllrs | 28.6.17 | Cllr Shaw reported to Mhotline | 29.6.17
|  |  | 17 | Waste on forest school washpool | 30.6.17 | Reported to SBC to clear as hazardous waste - needles. 30th |  |  |  | SBC visited and cleared site.
|  |  | 18 | Fly tipped waste on Ridgway Road | 30.6.17 | Clerk reported to Allbuild to clear 30th |  |  |  | Private land so CPC or SBC cannot clear

## July 2017
2017-07-01
H&S Impact H,M,L | Village Perception H,M,L | SBC division to deal |  | Request | Date issue received | CPC action | Date reported to Ward Cllrs | Ward Councillor/SBC action | Date Resolved | Other info
L | L | Highways | 1 | Road sign fallen over on New Road near Well Close | 2.7.17 | Reported to Ward Cllrs | 3.7.17 | Reported to Highways lagan 101003173723 |  | Old post removed and new post on order. 5.7.17
|  | Abandoned vehicle team | 2 | Abandoned vehicle in Windmill Piece | 2.7.17 | Reported to Ward Cllrs | 3.7.17 | Reported to abandoned vehicle team. DAV000006 | Vehicle gone
L | M | CPC | 3 | Canney area grass not cut | 4.7.17 | Reported to Allbuild to check | 5.7.17
|  |  | 4 | Overgrown hedge not cut for resident who pays SBC to do so. The Crescent | 3.7.17 | Reported to Ward Cllrs | 5.7.17 | SBC advised that start date for hedge cutting is 1st July so they will get to this area shortly. | 5.7.17 Resident advised
M | M |  | 5 | There's one area on Hodson Road between the Hodson turn off & Dairy Road (on this side) and one in High Street, Chiseldon which were marked but have yet to be done - the yellow paint marks have virtually disappeared. | 14.7.17 | Cllr Shaw reported to Mhotline
There's a pothole by a drain in Mays Lane which needs repair.
Lastly, could the road by the junction with Mays Lane, Turnball, and High Street be swept? Once again the leaves off the tree on one corner is blocking both the gutter & drains in High Street.
|  |  | 6 | Tree on SBC land on Marl Road overgrown into residents garden | 12.7.17 | Clerk reported to Ward Cllrs | Cllr Shaw asked Mhotline to check this out | Still WIP. Oct 2017
|  |  |  | Knotweed reported on exit of Chiseldon going to Og St George. |  | Clerk reported to Ward Cllrs | Cllr Shaw as Mhotline to check | SBC (Rob Core) advised nothing they needed to do as on farmers land.
7
|  |  | 8 | Gully on Hodson road needs clearing as rain water overflowing |  |  | Ward Cllr Shaw reported to Mhotline | Env drainage team cleared this
L | L |  | 9 | High Street sign knocked over | 30.7.17 | Clerk reported to Ward Cllrs | Eric reported to Mhotline 21.7. | Clerk chased Ward Cllrs Oct 2017
|  |  | 10 | machine sweeping of May Lane, Turnball and High Street |  |  | Done 17th July | 101003178410
|  |  | 11 | Rubbish outside house in marl road - needs to be cleared if on SBC land | 2017-07-01 | Clerk reported to Ward Cllrs to get land clarified as SBC land before proceeding | Cllr Shaw chased Mhotline 13.10.17 | Still trying to progress this, land is privately owned and not SBC land. Trying to get owner details

## August 2017
2017-08-01
H&S Impact H,M,L | Village Perception H,M,L | SBC division to deal |  | Request | Date issue received | CPC action | Date reported to Ward Cllrs | Ward Councillor/SBC action | Date Resolved | Other info
H | H | Highways | 1 | Zebra crossing in New Road the white markings are going fast and need repaint | 6.8.17 | Reported direct to WC's | 6.8.17 | Reporting to Mhotline 7.8.17. Clerk asked Cllr Shaw to chase 8.9.17. Cllr Chased 13.9.17 | Done 12.10.17
L | L | Highways | 2 | Bus bays ( yellow) in the main road A346, are very poor not need repainting both sides of the road, I think we asked over a year ago | 6.8.17 | Reported direct to WC's | 6.8.17 | Reporting to Mhotine 7.8.17 | Painted by SBC 23.8.17
L | L | Highways | 3 | Bus bays on B4005 New Road outside the back of the Esso station and bus stop need repainting | 6.8.17 | Reported direct to WC's | 6.8.17 | Reporting to Mhotline 7.8.17 | Done
M | M | Highways | 4 | Road resurfacing at High Street by Spar still not carried out. | 9.8.17 | Ward Cllr reported direct to Mhotline | 9.8.17 | Reported to Mhotline. Cllr Shaw still chasing 8.9.17 | 2 pot holes have been filled
L | L | Highways | 5 | Resident reported that Carrisbrook Terrace needs resurfacing | 9.8.17 | Clerk reported to Ward Cllrs | 10.8.17 | Will go on Highways list - may be some time
M | L | ? | 6 | Hedges overgrown in Draycott Foliat at Bus stop. |  | Cllr Shaw reported direct to Mhotline | 7.8.17. | Has requested site visit. | Bus stop to be moved so drivers can see it
L | L | CPC | 7 | Overgrown horse chestnut tree hanging into 11 Home Close | 10.8.17 | Clerk reported to Ward Cllrs | 10.8.17 | Asked Mhotline if CPC can cut back | Permission granted to trim tree

## Sept 2017
2017-09-01
H&S Impact H,M,L | Village Perception H,M,L | SBC division to deal |  | Request | Date issue received | CPC action | Date reported to Ward Cllrs | Ward Councillor/SBC action | Date Resolved | Other info
L | L |  | 1 | Fly tipping at the end of No5 Home Close on SBC land | 28.8.17 | Reported via WC | 28.8.17 | Cllr Shaw reported to Mhotline | 6.9.17 | Not fly tipping, residents tidying the nature area.
L | L |  | 2 | Badger sett - 4 Home Close | 28.8.17 | PW reported to WC | 28.8.17 | Cllr Shaw reported to Mhotline | Nothing to be done at present as no damage to drains
M | M |  | 3 | Rats seen at School grounds | 28.8.17 | Reported to WC |  | Cllr Foley contacted Headmaster | Head says rat catcher in attendance regularly and matter in hand | CPC are to investigate further. Ward Cllr Foley has visited the school and talked to the head and groundsmen who have a proper procedure in place with a rat catcher. Cllr Foley is waiting to receive the rat catchers report. There is a sewer cover outside but near the school grounds which could be where the rats are originating from.
L | L |  | 4 | Overgrown hedges alongside school. Further report from resident 13.9.17, passed to WC's also | 28.8.17 | Reported to WC |  | Cllr Foley contacted headmaster | Head reported that hedges ok. Cllr Shaw to walk area to see what hedges are overgrown and who needs to deal | Hedges appear to be currently causing no issue
H | H | Highways | 5 | Manhole covers on Mays Lane exposed and dangerous | 4.9.17 | Reported to WC | 4.9.17 | Cllr Shaw reported to Mhotline on 4th siting dangerous potholes. Clerk Chased Cllr Shaw 25.9.17. Cllr Foley chased Highways 25.9.17
|  |  | 6 | End of Ladysmith Road, the white road lines at private road have faded. Need repainting | 2.9.17 | Cllr Foley reported direct to Mhotline | 2.9.17 |  | Cllr Hill reported as re-painted 27.9.17
M | L |  | 7 | Grass needs cutting on path towards M4 J15 |  | Cllr Shaw reported direct to Mhotline | 1.9.17
M | L |  | 8 | Requested drain clearance on New Road by Meadow Stores before winter. | NA | Clerk reported to WC.s | 8.9.17 |  | Cllr Shaw initially advised to report direct to him when next a problem and he will arrange for SBC to clear. Queried this and Cllr Shaw has asked Mhotline to clear the drain before winter. | Drain was cleared earlier in the year. Was checked Sept 2017 and is not blocked.
M | L |  | 9 | The roadside hedges along the road from Badbury towards Liddington before and after the M4 motorway bridge require cutting back from the road. | 10.9.17 reported by resident | Clerk reported to WCs | 10.9.17 | Cllr Shaw chased Mhotline 12.10.17 |  | Clerk provided new photo of hedge obscuring road sign to Ward Cllrs on 11.10.17. Chased Ward Cllrs 6.11.17
M | L |  | 10 | At the junction of the Badbury road with the A346 Marlborough Rd there are trees on the right which growing too low and are obscuring the view of traffic coming up the hill from the M4. | 10.9.17 reported by resident | Clerk reported to WCs | 10.9.17
L | L | Martin Fry at SBC | 11 | Washpool path at Parsonage Farm overgrown | 13.9.17 reported by resident | Clerk emailed Martin Fry at SBC direct | 15.9.17 |  | WARP did some clearance too.
L | L |  | 12 | Dead badger on Hodson Road on the dip from Burderop Junction | 18.9.17 | Cllr Shaw reported direct to Mhotline | 18.9.17
|  |  | 13 | Back of Marl Road in Tatley Walk, waste reported. Ongoing investigations into ownership of the land | 19.9.17 | Cllr Shaw reported to Mhotline for removal | 19.9.17 |  | Ongoing - with SBC 9.10.17. Cllr Shaw chased 16.10.17. Land is privately owned but not by the people doing the fly tipping. Back to SBC for further advice 3.11.17
|  |  | 14 | 3 Damaged road signs. Canney Close, Saxon Mill and Burderop Barns "No through road" | DH reported to Clerk, Clerk reported to WCs 18.9.17 | Cllr Shaw reported to Mhotline 19.9.17 | 19.9.17 |  | Chased for resolution 9.10.17
M | L |  | 15 | Water gully on New Road at Meadow Stores prone to flooding. | Reported to WC's to ask them to clear it before winter. | 19.9.17 |  | 20.9.17 | Response: The road was cleaned on14 April 2016 as to our cleaning program. I raised an order for these particular gullies to be looked at. We found that they were ok and must have been due to the amount of rainfall on the day in question. We cleaned and checked the gullies again today when on site and the system was working.
L | L |  | 16 | Green road sign on A346 Badbury side damaged | 22.9.17 from David Hill | Reported to WC Sumner. |  |  | Cllr Hill reported this was fixed 27.10.17
|  |  | 17 | Speed watch sign missing from post as you enter Chiseldon from Hodson end. Cllr Rawlings asked CSW to report to SBC | 25.9.17 |  |  | SBC have no knowledge of removing this sign. CPC have not either
M | L | Highways | 18 | Hodson Road to Burderop Barns footpath/verge overgrown | 22.9.17 by David Hill | Clerk reported to W.Cllrs 25.9.17 |  | Landowner has cut their hedges back
|  |  | 19 | Draycott Road/Ladysmith Road crossroads overgrown - cant see road signs | 22.9.17 by DH | Clerk reported to W.Cllrs 25.9.17 |  |  | Cllr Hill reported at 19.10.17 meeting that this had been cut back.

## Oct 2017
2017-10-01
H&S Impact H,M,L | Village Perception H,M,L | SBC division to deal |  | Request | Date issue received | CPC action | Date reported to Ward Cllrs | Ward Councillor/SBC action | Date Resolved | Other info
M | L | Street Lighting | 1 | Repeat reporting of street light outside No. 33 Hodson Road | 6.10.17 by Cllr Shaw | NA, Chased Ward Cllrs 3.11.17 | Cllr Shaw reported to Mhotline 6.10.17 | Reported to Mhotline LAGAN 101003219298
M | L | Street Lighting | 2 | Street light in Mays Lane opposite Mays Cottage not working | Cllr Rawlings report to Clerk 9.10.17 | Reported to Ward Cllrs. Chased Wrd Cllrs 3.11.17 | Cllr Shaw reported 9.10.17 | Reported to Mhotline LAGAN 101003219973
|  |  | 3 | Request for grit bin at Draycott Foliat near bus stop | 9.10.17 | Clerk passed to W Cllrs 9.10.17 | Cllr Shaw reported to Mhotline 9.10.17. Clerk chased Ward Cllrs 27.10.17 |  | Seen in place 26.11.17
M | L |  | 4 | SORN vehicle on highway at Draycot Foliat | 13.10.17 | Clerk passed to W.Cllrs 15.10.17. Chased Cllr Shaw 2.11.17. Clerk also emailed PC Best for advice |  | Has been reported to DVLA who have issued a warning letter. Police have also advised owner of legal situation
M | M | Housing | 5 | Repair fence in Windmill Piece to stop dog getting into cemetery | Ongoing | Reported to Ward Cllrs for Housing dept 15.10.17 | Cllr Shaw reported to Mhotline 16.10.17 | CPC fenced in their side, and SBC Housing booked to repair the other side
H | H | Planning & Highways | 6 | Advertising banners at Esso Garage causing restricted view to A346 | 10.10.17 | Clerk has written to Esso Station 10.10.17. . Police have been informed. Clerk asked Ward Cllrs to chase enforcement & also asked Police to re-visit 4.11.17 | Ward Cllr Shaw has contacted planning enforcement and Highways at SBC 16.10.17 | Police are satisfied this is not a road danger (signs had been moved back from A3446)
L | L | Highways | 7 | Potholes at Badbury.
|  |  |  | Cllr Rawlings reported to Ward Cllr Sumner | 17.10.17 | Cllr Sumner reported to Mhotline 19.10.17 | lagan 101003221551
Drain broken at Pats Arms roundabout
M | L | Highways | 8 | Cllr Rawlings reported to Cllr Shaw | 17.10.17
L | L |  | 9 | 2 drains on High Street near Foundry Rise full of leaves and water near the top | 18.10.17
Clerk reported to Ward Cllrs
|  |  | 10 | Draycot Foliat bus stop work still outstanding. The bus stop pole is still to be moved and the sign in the middle of the hedge is still to be moved. | Cllr Hill chased Transport dept 17.10.17 | Work is to be done but no time scale given |  | Some work completed end of Oct 17. Cllr Hill chased the remainder 10.11.17

## Nov 2017
2017-11-01
H&S Impact H,M,L | Village Perception H,M,L | SBC division to deal |  | Request | Date issue received | CPC action | Date reported to Ward Cllrs | Ward Councillor/SBC action | Date Resolved | Other info
H | M | Highways | 1 | Road needs repairing, corner of CV Road and Windmill Piece | 13.11.17 | Clerk reported to Ward Cllrs. Clerk chased Ward Cllrs 12th Jan as no repairs yet. Sent another photo | 13.11.17 |  | See Marchs entry for this | Chased July 2018
L | M | Highways | 2 | Cllr Shaw reported damaged to verges on Hodson Road leading to Home Close after roadworks | 10.11.17 | NA | NA | Cllr Shaw reported to Mhotline lagan 101003227615 & 101003229011 | Verges repaired and new grips on order 22nd Nov
M | L |  | 3 | Turnball - 2 roadworks signs left in road after recent works by gas company | 10.11.17 | na | na | Cllr Shaw reported to Mhotline. Lagan 101003227615 | Removed 22nd Nov
M | L | Streetsmart | 4 | From Cllr Shaw: The warning sign indicating the road narrows as you approach Draycot Foliat from the Ogbourne St. George end is no longer visible as the hedging along the verge has completely covered it. Can the hedging be cutback or the sign taken out and resited? It's important because the road also bends as you reach Draycott Foliat where there are parked vehicles and a bus stop. | 14.11.17 | na | na | Cllr Shaw reported to Mhotline lagan 101003228019 | Paul Spice SBC reported cut back on 16th Nov
|  |  | 5 | Yellow bus bays on Draycott Road have been painted | 15.11.17
|  |  | 6 | New stop lines have been painted at Carrisbrook Terrace | 15.11.17
M | L | Highways | 7 | After motorcycle crash on A346, need to investigate and replace missing road sign | 15.11.17 | Reported to Ward Cllr Sumner | 16.11.17 | Ward Cllr Sumner has reported to SBC lagan 101003228545 with 10 working day SLA. New sign has been ordered
L | H | Housing | 8 | Windmill Piece - concern after survey was carried out by SBC, advising no new parking will be created & mistakenly advising that boulders would be put on grass verges. | 11.11.17 | Rob Anscombe is to feedback to CPC and SBC, and update residents with a hand delivered letter, |  |  | SBC have written to residents saying no changes will occur
L | L | Highways | 9 | Grass verge damaged by stagecoach bus on corner of New Road/Station Road | 17.11.17 | Reported to Ward Cllrs | 17.11.17 | Ward Cllr Shaw reported to SBC on 17th | Area has been blocked by cone and damage resolved
H | H |  | 10 | Chiseldon Firs camp entered. | 19.11.17 | Reported to Ward Cllrs | 19.11.17 | Ward Cllrs reported to SBC on 19th | Ongoing issue. Travelers left Jan 2018. Ongoing issue with cleanup and security
M | L |  | 11 | Drains at The Canney and Cambrai Road at Ridgway View need cleaning out, residents and Cllr Hill reported | 20.11.17 | Reported to Ward Cllrs | 20.11.17 | Reported as Lagan 101003228874 by Paul Page at SBC on 22nd Nov | DONE
|  |  | 12 | Verge parking making a mess at Cambrai Road - reported by resident | 20.11.17 | Clerk to investigate options. Requested advice from Ward Cllrs 27th | 6.12.17 | Letter written to resident asking them to not park on verge | Stones are now in place to block parking
L | L | Highways | 13 | Pothole at Badbury just before 30mph sign reported online to SBC | 27.11.17
L | L | Highways England | 14 | Potholes at J15 on A346 reported to Highways England online | 27.11.7
|  |  | 15 | Requested new SBC parking camera car visit school in Chiseldon | Note

## Dec 2017
2017-12-01
H&S Impact H,M,L | Village Perception H,M,L | SBC division to deal |  | Request | Date issue received | CPC action | Date reported to Ward Cllrs | Ward Councillor/SBC action | Date Resolved | Other info
L | L |  | 1 | Resident concerned over motorhome being lived in for past 2 weeks on Sambrai Road | 1.12.17 | Reported to Ward Cllrs | 1.12.17 | Asked Mhotline to get this investigated 4.12.17 | Still there 17th jan - Ward Cllrs advised again. Also damage to verges
|  |  | 2 | Overhanging trees in Norris Close reported | 2.12.17 | Reported to Ward Cllrs | 3.12.17 | Ward Cllr Shaw reports back that the trees will be trimmed by SBC
|  |  | 3 | Overhanging tree reported in Home Close near nature area | 1.12.17 | Reported to Ward Cllrs | 3.12.17 | Ward Cllrs requested photos, asked resident for these 4.12.17
|  |  | 4 | 2 blocked drains on Station Road - near Landmark and near Spar | 6.12.17 | Reported to Ward Cllrs | 6.12.17 | Ward Cllr Shaw reported to Mhotline 6.12.17
|  |  | 5 | Ward Cllr Shaw reported direct to Mhotline:
Although the verge was cleaned up after the gas board had finished their work it's once again mud as HGVs and tractors make little or no effort to stay on the tarmac. There's a widening gap between the edge of the tarmac and the verge. The grips still haven't been cleared. In places the verge isn't much wider than 50cms. and a deep drainage ditch runs alongside. Can you ask Streetsmart/Highways to visit and see if anything can be done please?
In addition the Mr. & Mrs. R. who live in the corner bungalow- who own the verge have complained that it has already been damaged following the gas board who reinstated it after the recent work in the road.
They're are asking about "kerbing", not for the first time, to protect it. I can understand their concern.
M | L | Highways | 6 | Tree branch across road near M4 bridge | 13.12.17 | Reported to Ward Cllrs | 13.12.17 | Ward Cllr Shaw asked for tree to be cleared ASAP 13.12.17 | Tree removed
M | L | Highways | 7 | Road towards M4 bridge has mud and leaves on road | 13.12.17 | Reported to Ward Cllrs | 13.12.17
M | L | NA | 8 | Broken tree branch on path by Butts Road cemetery | 13.12.17 | Clerk asked contractor to remove |  | Removed by CPC contractor
L | L |  | 9 | Trees in nature close in Home Close too close to property | 6.12.17 | Reported to Ward Cllrs | 11.12.17 | WC Shaw was dealing with this, with the resident
|  |  | 10 | Fly tipping Hayhouse Lane - hazardous waste from sanitary boxes. | 15.12.17 | Reported to Ward Cllrs as hazardous waste so SBC to deal | 15.12.17 | Ward Cllr reported to HMOtline for ASAP clearup 15th Dec | Cleared 16th Dec
|  |  | 11 | Ward Cllr Shaw to request Downes Road has a grit box. Allbuild spread some grit during cold weather | 13.12.17 |  |  |  | Done
|  |  | 12 | Resident Mrs E, reported further issues with corner of Hodson Road entering Chiseldon - vehicles not taking care and excessive speed. | 15.12.17 | Clerk advised this is on the PC's transport list and also reported to Ward Cllrs | 18.12.17 | Ward Cllrs replied to Mrs E to say they are trying to get speed limits in the area reduced as a long term project and will continue to work towards some action.

## Jan 2018
2018-01-01
H&S Impact H,M,L | Village Perception H,M,L | SBC division to deal |  | Request | Date issue received | CPC action | Date reported to Ward Cllrs | Ward Councillor/SBC action | Date Resolved | Other info
M | L | Mhotline | 1 | Abandoned vehicle on A346 at Chiseldon Firs site | 3.1.18 | Reported to W.C's | 3.1.18 | Reported to Mhotline 3.1.18 | 2018-01-01 | Now removed
|  |  | 2 | Trees need trimming back - presumed at Wheatley House - to check first. No lighting also on footpath from Canney Close to Spar. Also leaves on ground, resulted in fall. | 23.12.17 | Reported leaves to probation team to clear and SBC for lighting issue | 28.12.17 | Reported to Mhotline 28.12.17 |  | Also asked Allbuild to clear any moss from this area. Clerk wrote to home owners on 15th Jan asking them to trim trees | Trees to be cleared back in summer
M | M |  | 3 | Potholes: | 2.1.18 | NA | 2.1.18 | W.C's reported direct to Mhotline 2.1.18
There are two new but large potholes on Hodson Road between Burderop Junction and the entrance signs to Chiseldon village:- a. Approximately 50 mtrs from the Burderop Junction in the middle of Hodson Road.
b. Approximately 100 mtrs. from the entrance signs to the village in the middle of the road.
Lastly as you turn left into Hodson Road at Burderop Junction there's a fairly large area of tarmac on that lefthand side near to the verge which is breaking up and will need patching again.
L | L |  | 4 | New Road layby verges churned up - needs repairing or tarmacking | 2017-12-01 | Clerk reported to W.C's | 4.1.18 | Eric S already reported
L | L |  | 5 | Verges at Castle View road from New Road churned up. Need repairing or tarmacking | 2017-12-01 | Clerk reported to W.C's | 4.1.18 | Eric S already reported
M | L |  | 6 | Pre-stop sign at Burderop junction twisted. Need repairing or moving to safer location | 2017-12-01 | Clerk reported to WC's | 4.1.18 | Eric S reported to SBC 5.1.18
M | L |  | 7 | A346 Badbury side at bus stop very dark, needs a street light | 2017-12-01 | Clerk reported to WC's | 4.1.18 | Gary S reported to SBC 5.1.18
M | M |  | 8 | Gary S reported issues with road surface on Badbury Road from A346 | NA | NA | NA | 5.1.18
M | M |  | 9 | There's a large pothole in High Street, Chiseldon that needs repair. Turning left into High Street from Turnball it's about 12mtrs. down the slope, almost opposite on the lefthand side is a blocked drain and lastly the centre of the road especially around no.11 past The Spar shop is breaking up in several places. | 6.1.18 | NA | NA | Eric S reported direct to SBC 6.1.18
|  |  | 10 | From Ward Cllrs;
M | L |  |  | MAYS LANE UPDATE FROM HIGHWAYS | 11.1.18
I have looked at the location again this morning and the road has now been swept which does help as it uncovers my drains.
We visited this location before Christmas to clean gullies in this area and since then more leaf problems.
On my visit I found all gullies at the bottom of the hill are fine I took photos for records.
I did however notice the three usual suspects at the junction of Turnball could do with some attention again. The location of these three would however not cause any flooding as water would run down the kerb line to the next clear gully.
We last did a full village clean April 2016 and will soon be programed for another on the system.
I will get the lads to attend these problem ones again shortly.”
M | M |  | 11 | Windmill Piece new grit bin | 15.1.18 | Reported to WCs | 17.11.8 | WC Shaw has reported and is waiting to hear back on progress | New bin to be in place by 26th Jan | Bin in place
M | L |  | 12 | Vehicle activated sign on Hodson Road not working | 18.1.18 | Reported to WCs | 18.1.18 | WC reported this to Mhotline
M | L |  | 13 | Street lights on Highstreet and Draycott Road not working | 22.1.18 | Reported to WCs | 22.1.17 | WC Shaw reported 22.1.18 | Column 8 Mays Lane Confirm Job number 1010032. Jadu MHG000416. Column 12 Draycott Road Confirm Job number 1010033. Jadu MHG000417
L | L |  | 14 | Aisne Road sign in Ridgeway View damaged | 19.1.18 | Reported to WCs | 19.11.18 | WC reported to SBC 22.1.18
L | L |  | 15 | Bericote Lane Badbury. Overgrown hedges & trees, fire hydrant obscured and falled tree in turning circle. | 27.1.18, Mr H | Reported to WCs | 29.1.18
L | L |  | 16 | Trench outside Chapel needs weeding | 29.1.18 | Clerk asked probation team to do this
M | L |  | 17 | Potholes on Ridgeway Road opposite Farm Shop car park. |  |  |  | WC Shaw reported direct to SBC 27.1.18
L | L |  | 18 | Reported leaf debris on road at Ridgeway View near Cambrai Road, and provided photos | 29.1.18 | Reported to WCs | 29.1.18 | WC Shaw reported to Mhotline 31.1.18 | Done 31.1.18
L | L |  | 19 | Resident request. Grit box for rear of Marlborough Road and also a street sign erected | 29.1.18 | Reported to WCs | 29.1.18 | WC Shaw reported to Mhotline 31.1.8 |  | Previous request for road sign here was rejected by SBC
M | M |  | 20 | Potholes: On A346 as you come up the hill from J15 On A346 as you go down the hill towards J15 New Road between the Patriots Arms roundabout and the zebra crossing. Station Road – have been marked in yellow – does this mean they are scheduled in? Corner of Windmill Piece with Castle View Road - the yellow paint has faded away on this area that was previously marked. | Resident reported to Clerk 27.1.18 | Reported to WC's 29.1.18
L | L |  | 21 | Verges damaged on Marl Road after Butts Road works | Resident reported to Clerk 31.1.18 | Reported to WCs 31.1.18 | 31.1.18 | WC Shaw reported to Mhotline | 31.1.18
|  |  | 22 | Request for improved lighting to Strouds Hill carpark | 29.1.18 | Reported to WCS 31.1.18 | 31.1.18 | WC Shaw reported to Mhotline 31.1.18
|  |  | 23 | The Parish Council have reported potholes on both sides of Plough Hill on the A346 and I've just driven along Hodson Road from Chiseldon to Burderop Junction and there new potholes just outside Chiseldon, either side of the turn off to Hodson and several others as you approach the junction by the Toll House. There's also one large one on Draycot Road just before the crossroads at The Ridgeway. |  |  |  | Cllr Shaw reported direct to Mhotline 31.1.18
|  |  | 24 | Leaf matter cleared from the edges of Butts Road placed on verges/banks by contractor, request they clean this up |  | Clerk reported to WCs | 31.1.18 | WC Shaw reported to Mhotline 31.1.18

## Feb 2018
2018-02-01
H&S Impact H,M,L | Village Perception H,M,L | SBC division to deal |  | Request | Date issue received | CPC action | Date reported to Ward Cllrs | Ward Councillor/SBC action | Date Resolved | Other info
|  |  | 1 | The area around the junction of High Street, Church Street and Butts Road suffers damage to walls and signage due large HGVs trying to gain access to Butts Road. They find they can't and have to reverse down to Station Road or try and turn round at the junction usually causing damage - eg High Street road sign. | NA | NA |  | WC Shaw reported direct to Mhotline 10.2.18 |  | Sign replaced Feb 2018
One reason for this is that the restriction sign in High Street can't be seen until the HGV is in the road due to its position & height. It needs to be moved to a more prominent position.
Can this be looked into please?
Secondly at the site meeting on 05/12/17 whilst discussing issues around the Butts Road resurfacing I was promised by Streetsmart that the damaged High Street sign, the cul de sac sign by the bungalow in Church Street ( currently the only one ), and the church sign would be replaced plus an additional cul de sac sign. The idea being to reduce the level of damage currently being experienced as the owner of 1, High Street - Mr. Graham Rivers - will tell you.
I had thought both these matters were being attended to following the site meetings but apparently this is not the case.
L | L | CPC | 2 | Residents report via SBC on waste on A346 from J15 | 7.2.18 | Requested Allbuild did litter pick 12.2.18
|  |  | 3 | Drain on New Road near corner with Turnball blocked | 14.2.18 | Clerk reported to WC's | 14.2.18
|  |  | 4 | At the end of last week Mays Lane, Chiseldon was closed temporarily by the Water Board to repair a water leak from Chiseldon House Hotel. Warning signs were set up in the above roads. The work has been completed but the signs remain and those in Turnball & New Road are partly in the road causing vehicles to move across the centre - they are dangerous- can they please be moved asap? |  |  |  | WC Shaw reported direct to Mhotline 13.2.18
|  |  | 5 | Clerk asked WC's to find out who cleared tree at 39 New Road during the storms | 12.2.18 | Clerk reported to WCs | 12.2.18 | WC Shaw reported to Mhotline 12.2.18 |  | SBC unable to answer for certain as crews take down trees on patrol after a storm, resident advised.
|  |  | 6 | Note from Nigel Hale at SBC as to when the bus stop changes at Draycott Foliat will be carried out: "The relocation of the bus stop from one side of the hardstanding to the other end is planned to be done by the Highways Maintenance team in March. This is part of a programme of other bus stop maintenance work." | 2018-02-01 | Info from Cllr Hill |  |  |  | Due 5th March 2018
|  |  | 7 | Can you report number of pot holes in New Road, in the surface put down 3 years ago. | 12.2.18 | Clerk reported to WCs | 14.2.18 | WC Shaw reported to Mhotline 14.2.18 | SBC replied to say patched on 16.2.18 MHG0000709
from Cllr Hill
The Location is the left hand side coming from the Esso Station after the turn into Station road
after the turning to the Plymouth B Church, and before the Build Out, two patches of pot holes
getting bigger by the day, as the frost has got into the base of the road now.
|  |  | 8 | Can you report number of pole holes in the Main road A346, as the all the road surface part in in | 12.2.18 from Cllr Hill | Clerk reported to WC Gary Sumner | 14.2.18 | WC Sumner reported to SBC 14.2.
[8 empty] | MHG000703 | Reply from SBC to say some potholes filled and waiting for others to be booked in. From Chris Ball 20/2/18
Ridgeway Ward can you report the Borough Cllr Gary Sumner please,
The location is slow lane up the hill on other side to Plough Pub and its in right hand side of that
lane up to top of the hill, it has been affected cold weather of last few weeks, and traffic is going
over to the fast lane, when you drive over theses pot holes,
Some are large pot holes and patching maybe the answer, with the amount of traffic using the main
road.A346.
|  |  | 9 | Downs Road grass verges damaged by vehicles parking. Resident reported | 15.2.18 | Clerk reported to WC's 19.2.18 and wrote letters to the residents concerned | 19.2.18 | WC Shaw reported to Mhotline for repairs 19.2.18 | WC Shaw advised this has been added to SBCs works list. 21.2.18 | Cllr Shaw reports that this will be repaired
|  |  | 10 | 2 street lights not working. Junction of Mays Lane, High Street, Turnball. | 19.2.18 | Clerk reported to WC's 19.2.18 | 19.2.18 | WC Shaw reported to Mhotline 19.2.18 | MHG000784 | Case Closed as order raised for new light to be fitted
Slipper Lane/Turnball junction
|  |  | 11 | Street lights not worknig: | 23.2.18 | Clerk reported to WCs 23.2.18 | 23.2.18
|  |  |  | On New Road, opposite the main entrance to the Chiseldon House Hotel – on a wooden pole. | 26.2.18 | Clerk reported to WC's | 26.2.18 | Job no 1010522 |  | MHG000857. Chased 21st March
|  |  | 12 | On Mays Lane, going up the hill towards New Road, opposite the thatched cottage. On a wooden pole – hidden by quite a lot of undergrowth and foliage – quite hard to spot I’ve been told. | 26.2.18 | Clerk reported to WCs | 26.2.18 | Job no 1010523 |  | MHG000857. Chased 21st March
|  |  | 13 | Potholes - Hodson Road, Chiseldon | 14.2.18 | WC Shaw reported direct | 14.2.18
a. Just outside Chiseldon on the road to Hodson turn off several in the centre of the road.
b. One in centre of road in the dip near Dairy Road.
c. Two - one large near postbox before junction with Brimble Hill.
|  |  | 14 | Potholes - . New Road, Chiseldon Two - On field side just beyond "build out" going towards A346 Marlborough Road. | 14.2.18 | WC Shaw reported direct | 14.2.18

## March 2018
2018-03-01
H&S Impact H,M,L | Village Perception H,M,L | SBC division to deal |  | Request | Date issue received | CPC action | Date reported to Ward Cllrs | Ward Councillor/SBC action | Date Resolved | Other info
|  |  | 1 | Chased road repairs needed to corner of Windmill Piece and Castle View Road | 7.3.18 | Reported to WCs | 7.3.18 |  |  | Chased again July 2018
|  |  | 2 | Chased resident request for hedge cutting on Plough Hill (CPC don’t do this). Asked to go back to SBC | 7.3.18 | Reported to WCs | 7.3.18
|  |  | 3 | WC Shaw followed up with Mhotline on ownership of bank at Mays Lane | 6.3.18 | NA | NA | WC Shaw reported to Mhotline |  | Cottage on opposite of road owns bank, CPC cut hedge as part of parishing. Need to determine who deals with brambles
|  |  | 4 | Reported road surfac damage at Castle View Road near the Orchard | 9.3.18 | Reported to WCs | 9.3.18 | WC Shaw reported to Mhotline 9.3.18
|  |  | 5 | Passed on residents comments on Marl Road near Butts road grass verge damage after Butts Road resurfaced | 12.3.18 | Reported to WCs | 12.3.18
|  |  | 6 | Reported left behind equipment from Thames Water at Badbury | 12.3.18 | Reported to WC Sumner | 12.3.18 | WC Sumner reported to Thames Water 12.3.18
|  |  | 7 | There are two areas of potholes in the centre of the B4005 between Chiseldon & the junction with the road to Hodson which attention. | NA | NA | 12.3.18 | WC Shaw reported direct to Hhotline
|  |  | 8 | Grit bins need filling: Top of Mays Lane near New Road Opposite new vicarage in Butts Road By junction of Turnball & Slipper Lane. | NA | NA | 18.3.18 | WC Shaw reported to Mhotline
|  |  | 9 | Broken street light - Slipper Lane/Turnball junction | 15.3.18 | Reported to WCs | 15.3.18 | WC Shaw reported to Mhotline 15.3.18 |  | Fixed 20.3.18
|  |  | 10 | Litter dropped at Hodson after SBC collection service | 15.3.18 | Reported to WCs | 15.3.18 | WC Shaw reported to Mhotline | Done 20.3.18 | Mhotline spoke to the rubbish collection team concerned
|  |  | 11 | Resident reuquest on front garden tidy on Station Road | 15.3.18 | Reported to WCs | 15.3.18 |  |  | Didn’t get feedback but front of property appears to be more tidy.
|  |  | 12 | Requested SBC cut hedge at Draycott Foliat parking area | 21.3.18 | Reported to WCS | 21.3.18 | Cllr Cathy Martyn requested Mike Ash at SBC check ownership and arrange a cut before nesting season. 28.3.18
|  |  | 13 | Road signs on A346/New Road junction - request for them to be removed | 26.3.18 | Reported to WCs | 26.3.18 |  |  | Done
|  |  | 14 | Abandonded white Asra van in Strouds Hill car park reported | 26.3.18 | Reported to WCs | 26.3.18 | WC Shaw reported to Mhotline 26.3.18 MHG001245. SBC to start the process for removal 28.3.18 |  | removed
|  |  | 15 | Can you please pass on a report for a dangerous pothole that’s appeared on the first bend to Draycott it’s on the going towards Draycott side opposite the lane that goes across to Barbury castle. If you have to move over to avoid oncoming cars you are likely to go into it and come out with only 3 wheels!!
|  |  |  | Plus the recently repaired holes at the Draycott road crossroads have reappeared after the snow. | 23.3.18 | Reported to WCs | 26.3.18 | More potholes:-
a. along Hodson Road
b. in High Street Chiseldon - middle of the road near the Spar Shop.
c. on the Ogbourne Road coming from Draycot Road by the the first bend where there's an unnamed road off to the right.
|  |  | 16 | reported missing wooden post from Strouds Hill carpark | 23.3.18 | Reported to WCs | 23.3.18 | WC Shaw reported to Mhotline 26.3.18 |  | Replaced Sept 2018
|  |  | 17 | Reported potentially unsafe tree in strouds hill green area near the carpark | 26.3.18 | Reported to WCs |  | WC Shaw reported to Mhotline 26.3.18
|  |  | 18 | Verge damage at Ridgeway View reported again | 23.3.18 | Reported to WCs | 26.3.18
|  |  | 19 | Bottles dumped at Draycot Foliat reported to Allbuild | 28.3.18 | Clerk reported to Allbuild | 28.3.18 | To be collected on 29th |  | DONE

## April 2018
2018-04-01
H&S Impact H,M,L | Village Perception H,M,L | SBC division to deal |  | Request | Date issue received | CPC action | Date reported to Ward Cllrs | Ward Councillor/SBC action | Date Resolved | Other info
L | M |  | 1 | Potential fly tip near 5 Butts Road - need to find owner of land | 8.4.18 | Asked WCs to find owner of land | 8.4.18 | Requested land registry details | 2018-04-01 | Private land so nothing CPC or SBC can do.
M | M | Highways | 2 | Reported road deterioration on Mays Lane | 8.4.18 | Reported to WCs | 8.4.18 |  |  | Possibly scheduled for fixing Spring 2019
M | M | Highways | 3 | Updated Ward Cllrs of state of Windmill Piece road at the entrance. Requested by resident | 14.4.18 | Reported to WCs | 14.4.18 | WC Shaw reported to Mhotline 17.5.18 |  | Chased July 2018
M | M | Highways | 4 | Potholes have been reported on/in the following roads: | 17.4.18 | Reported to WC's | 17.4.18 | WC Shaw reported to Mhotline 17.5.18
Plough Hill on the A346 - several potholes mostly in the centre of the road up from Junction 15.
|  |  |  | Turnball - opposite the old Chapel & lower down around the junction with Slipper Lane. | [5 empty] | Spring 2019 perhaps
|  |  |  | Castleview Road - by no.29. |  |  |  |  | Castle View Road pothole filled
M | M | Highways | 5 | WC Shaw reported following potholes:The first 30mtrs. of this road from its junction with New Road is full of potholes and the grass verge is even worse with a rut in it about 300mms. deep & about 1.5 mtrs. long. | 17.4.18 |  |  | WC Shaw reported direct to Mhotline 17.4.18
M | M | Highways | 6 | No HGV sign for High Street to be moved to corner of Station Road and High Street so can be seen coming down Mays Lane and Station Road. (Sign at other end of Butts Road was also discussed) | 18.4.18 |  |  | Site visit from WC Shaw, Cllr Rawlings and SBC Highways to decide best position. | Moved to new location
M | M | Highways | 7 | . Turning left into Hodson Road from Brimble Hill there's a large pothole close to a postbox. It's an extension of one filled earlier during the cold spell. | 18.4.18 |  |  | WC Shaw reported direct to Mhotline 18.4.18
2. Several in the centre of the road about 200mtrs. from the village entry sign to Chiseldon.
M | M | Highways | 8 | High Street potholes reported direct by WC Shaw - MHG001248 (Near New Road) | Unknown |  |  | Reply from SBC: I have raised an order to have these filled within the next couple of days Kind Regards Chris. Chris Ball
|  |  | 9 | Japanese knotweed reported on road towards Og St George | 26.4.18 | Reported to WCs | 26.4.18 | Reply from SBC is that this is on private land so landowner needs to deal with it. Will monitor and contact land owner if out of control
|  |  | 10 | Windmill Piece road update |  |  |  | WC Shaw advised on 20th April that surface to be patched and pot holes repaired on this road - date unknown. |  | Chased July 2018
|  |  | 11 | Requested old signs be collected: | 25.4.18 | Reported to WCs | 25.4.18 | WC Foley will report to Mhotline
Badbury side – as you come off the M4 J15 roundabout on the verge on the left
Badbury side – on the actual verge of the roundabout junction– diversion sign still upright – not sure if there are any diversions still in place?
Badbury side – by the bus stop
Badbury side – at the T junction of the A346 and New Road – by the directional signs.
Chiseldon side – by the carpark exit of the Plough pub
Chiseldon side – sign frame by the cash machine of the Esso station

## May 2018
2018-05-01
H&S Impact H,M,L | Village Perception H,M,L | SBC division to deal |  | Request | Date issue received | CPC action | Date reported to Ward Cllrs | Ward Councillor/SBC action | Date Resolved | Other info
L | L | Streetsmart | 1 | Graffiti on chiseldon firs barriers | Clerk reported 4.5.18 | Reported to WCs | 4.5.18 | Cllr Foley to report to Mhotline | Removed in May
|  | Highways | 2 | Pothole on Station Road near Landmark hotel | 12.5.18 | Clerk reported to WCS | 12.5.18 | Cllr Mattock to report to Mhotline 13.5.18
|  | Highways | 3 | Clerk chased up pothole outside no29 Castle View Road | 16.5.18 | Chased WCS | 16.5.18 | Ward Cllr Foley to chase | Filled
|  | Highways | 4 | Resident chased potholes at A346 roundbout and road to Hodson. | 16.5.18 | Chased WCS | 18.5.18 | Ward Cllr Foley to chase | Hodson Road filled
|  | Streetsmart | 5 | Resident commented on grass verges not cut near highways. Reported via Streetsmart and passed to CPC. Clerk returned to WC's asking for SBC case to be re-opened as SBC deal with 1 meter verge of grass on highways | 16.5.18 | Passed back to WCS | 18.5.18 | Ward Cllr Foley to return case to S.Smart | Mowed 4 times a year under SBC Rural verges scheme. Resident adviced by WC Foley

## June 2018
2018-06-01
H&S Impact H,M,L | Village Perception H,M,L | SBC division to deal |  | Request | Date issue received | CPC action | Date reported to Ward Cllrs | Ward Councillor/SBC action | Date Resolved | Other info
M | L | Highways | 1 | Broken manhole cover on New Road near build out | 3.6.18 - chris R | Reported to W/C | 3.6.18 | Reported to Highways | Fixed 7.6.18
M | L | NA | 2 | Overgrown tree on Sambrai Road | 8.6.18 - resident | Asked our contractor to look and quote | 8.6.18 | Reported to WCs 8th June |  | SBC are to remove this as on their land
M | L | Streetsmart | 3 | Bent lamppost on Pats roundabout | 11.6.18 - Chris R | Reported to Ward Cllrs | 11.6.18 | Already passed to Streetsmart | Booked in for replacement | Fixed 30.7.18
H | L | Highways | 4 | Issue with vehicles double parking on New Road layby (medical emergency exit needed) | June | Reported to WCs | June | WC Mattock said SBC officers didn’t have a solution so he was going to do a site visit. 5.7.18 |  | No solution from SBC as they have no powers to deal with this.

## July 2018
2018-07-01
H&S Impact H,M,L | Village Perception H,M,L | SBC division to deal |  | Request | Date issue received | CPC action | Date reported to Ward Cllrs | Ward Councillor/SBC action | Date Resolved | Other info
|  |  | 1 | Brambles on High Street near foundry rise at walking level | 28.6.18 | Reported to WCs | 4.7.18 | WC Mattock reported to SBC |  | Cut back
|  |  | 2 | Trees in garden of house on High Street overgrown and hanging into neighbours garden | 21.6.18 | Reported to WCs and Cllr Sunner to chat to owner | 4.7.18 | WC Mattock has asked officers to investigate |  | Not on SBC land - private issue
|  |  | 3 | Damaged road sign at T junction of Ridgeway, Draycott Road and Ladysmith Road | 2.7.18 | Reported to WCs | 2.7.18 | WC Mattock to report |  | Replaced
|  |  | 4 | New Road inspected - report from Highways: I marked 3 carriageway patch jobs between the shop and the Patriots arms, these should be done within 6 weeks | 28.6.18 | Reported to WCS | 29.6.18 | This is the reply from SBC after WC Foley reported it. Chased 10.8.18
|  |  | 5 | Mays Lane inspected - report from Highways- "I inspected Mays lane today and have raised jobs for a pothole and a patch to be done, the carriageway patch is next to a manhole which is slightly exposed because of that part of the road sinking slightly. I also noticed a water leak to the front of May cottage and have sent Thames water a section 81 e.mail.” | 28.5.18 | Reported to WCs | 29.6.18 | This is the reply from SBC after WC Foley reported it
|  |  | 6 | brown road signs on A346 and dead end sign at church street reported as damaged | 11.7.18 | Reported to WCs | 11.7.18 |  |  | Church street sign fixed
|  |  | 7 | Pathway from Home Close - hedges reported as overgrown. Asking SBC to find out who maintains these. |  | Reported to WCs | 13.7.18 | WCs will ask 21.7.18 |  | Privately owned - SBC to send a letter
|  |  | 8 | Bus shelter on Station Road damaged. | 28.7.18 | Cllr Hill reported to Adshel | 28.7.18 | Adshel have fixed |  | Fixed 1.8.18
|  |  | 9 | Graffiti on barriers at Chiseldon Camp entrance | 28.7.18 | Reported to WCs | 28.7.18 | WC Mattock reported for cleaning 30.7.18
|  |  | 10 | Reported to WCs that path on The Canney is flooded each year as pavement dips | 25.7.18 | Reported to WCs | 25.7.18 | WC Foley advised they will action this |  | Chased 30th Aug. Chased 27th Sept. Chased Dec
|  |  | 11 | Green countdown signs on A346 to M4 obscured by greenery | 25.7.18 | Reported to WCs | 25.7.18 | WC Foley advised she will report |  | Chased 30th Aug
|  |  | 12 | 30mpg sign in Hodson lost in undergrowth and sign leaning | 25.7.18 | Reported to WCs | 25.7.18 | WC Foley will report

## Aug 2018
2018-08-01
H&S Impact H,M,L | Village Perception H,M,L | SBC division to deal |  | Request | Date issue received | CPC action | Date reported to Ward Cllrs | Ward Councillor/SBC action | Date Resolved | Other info
|  |  | 1 | Metal bollard in Slipper Lane keeps being knocked over. | 10.8.18 | Reported to WCs | 10.8.18 | Reported to SBC | 23.8.18 | Fixed
|  |  | 2 | Norris Close bollard to be re-instated - request | 18.8.18 from Cllr Rawlings | Direct to Ward Cllrs | 18.8.18 | WC Foley to report to SBC for consideration |  | CPC to consider this work when Norris Close layby is installed in 2019. SBC have no record of them installing a post.

## Sept 2018
2018-09-01
H&S Impact H,M,L | Village Perception H,M,L | SBC division to deal |  | Request | Date issue received | CPC action | Date reported to Ward Cllrs | Ward Councillor/SBC action | Date Resolved | Other info
M | L | Highways | 1 | White lines on Plough Hill near roundabout need repainting | 10.8.18 by Cllr Hill | Reported to WCs | 10.8.18 | Reported to Highways. Update on 12th - need to find funds to hire in a contractor to do this |  | Cat eyes to also be replaced as broken
L | L |  | 2 | 1 Crescent hedge needs cutting by SBC | 10.8.18 Cllr Rawlings | Reported to WCs | 10.8.18 | WCs to ask SBC to action |  | DONE in Oct.
H | L | Housing | 3 | Vehicle on New Road driving over verges to get to self made driveway | 10.8.18 by Cllr Rawlings | Reported to WCs | 10.8.18 | WC Foley to report to Housing | Housing to talk to resident about this. | Resolved. Was only a temp arrangement
M | L |  | 4 | Gas leak in Canney Close resulted in street light being removed. Column no.2. SBC will replace column and need to make sure they put back the neighbourhood watch sign. Cllr Hill contacted SBC direct | 21.9.18 by Cllr Hill | Reported to WCs 24.9.18 | 24.9.18 | WC Foley to follow this up. |  | Post in place - elec supply to be restored on 17th Oct
|  |  | 5 | Hodson - leaning traffic light pole over the M4 bridge and overgrown trees covering traffic lights on bridge | 21.9.18 in council meeting | Reported to WCs 21st | 21.9.18 | WC Foley advised has been reported to officers

## Oct 2018
2018-10-01
H&S Impact H,M,L | Village Perception H,M,L | SBC division to deal |  | Request | Date issue received | CPC action | Date reported to Ward Cllrs | Ward Councillor/SBC action | Date Resolved | Other info
L | L | Highways | 1 | Kerb stone broken on New road by Meadow Stores. From Cllr Rawlings | 9.10.18 | Reported to WCs | 10.10.18 | Reported to SBC 10.10.18 |  | Job MHG003924 logged 12.10.18
|  |  | 2 | Safe crossing place on A346 by Butts Road for bus users requested by Cllr Hill | Ongoing but officially reported 8.10.18 | Reported to WCs | 10.10.18 | Reported to SBC for consideration 10.10.18 |  | On SBC list of works. Wont be reviewed until Autumn 2019 by SBC
|  |  | 3 | Pothole on A346 coming off M4 J15 exit by Cllr Hill | 8.10.18 | Reported to WCs | 10.10.18 | Reported to SBC Highways 10.10.18 |  | Will be done as part of line painting work on this stretch of road
|  |  | 4 | Waiting for Draycott Close parking area in Draycot Foliat to be swept | Ongoing | Asked WCs to chase this 10.10.18 | 10.10.18 | BM forwarded to officers for action 10.10.18 | Done in Nov
|  |  | 5 | Post on corner of Slipper Lane bent | 12.10.18 from Clerk | Reported to WCs | 12.10.18 | Cllr Foley reporting for repairs 12.10.18 |  | Repaired
|  |  | 6 | Reported that Manor Rise still needs road tarmacking | 12.10.18 from Clerk | Reported to WCs | 12.10.18 | Cllr Foley to ask Planning for developers schedule to do this work |  | Chased in Dec. Waiting for developers to finish work so SBC can sign S38 agreement to adopt the road | Ongoing - Developers not ready to complete work for S38 to be signed.
|  |  | 7 | Street lighting for Draycott Close in Draycot Foliat - requirement to have lights installed as area is dark. Also car park sweep required by SBC | Ongoing | Reported to WC's as official request |  | WC Mattock refered to SBC for consideration 23.10.18 |  | Car Park swept in Dec
|  |  | 8 | Overgrown pampass grass on Draycot Road, blocking exit view from The Crescent | Ongoing | Reported to WCs after sending Parish letter to resident which had limited success | MHG003898 | Overgrown vegetation letter sent to home 15.10.18. SBC have also sent a vegetation letter to the home owner |  | Grass has been cut back
|  |  | 9 | Column 1 street light in Mill Close not working | 22.10.18 | Reported to WCs | 22.10.18 | WCs to report to SBC dept. |  | Fixed
|  |  | 10 | 2 blocked drains on High Street near Foundary Rise | 29.10.18 from Clerk | Reported to WCs | 29.10.18 |  |  | Cleared
|  |  | 11 | Mays lane has 4 drains blocked and | 29.10.18 from Cllr Rawlings | Reported direct to WCs | 29.10.18 | WCs to report to correct SBC dept
Urgently need the Road Sweeper
Vehicle doing both sides
The high Street has a drain blocked
On the right half way up by the entrance that take you through to School close
|  |  |  | Query over elec car charging point for a private property - ref John Alder Close | 1.10.18 | Reported to WCs to ask the question |  |  |  | Chased WCs 2.1.19 and WC Mattock will chase

## Nov 2018
2018-11-01
H&S Impact H,M,L | Village Perception H,M,L | SBC division to deal |  | Request | Date issue received | CPC action | Date reported to Ward Cllrs | Ward Councillor/SBC action | Date Resolved | Other info
M | M | Street Lights | 1 | Street light on bend on butts road broken. Paul S reported | 2.11.18 | Reported to Ward Cllrs | 2.11.18 | WC Mattock reported to SBC | Fixed | MHG004163
L | L | Highways | 2 | 5 blocked drains in Station Road/Strouds Hill area reported by C Wilkinson | 7.11.18 | Reported to WCS | 7.11.18 | WC Mattock reported to SBC | Cleared but may need doing again
M | M | Street lights | 3 | Street light broken at Mays Lane, plus ivy needs removing from lamp post as blocking light. Reported bt Cllr Rawlings | 12.11.18 | Reported to WCS | 12.11.18 |  |  | Chased with WC Mattock at EGPA meeting on 18th fe b 19
|  | Street lights | 4 | Street light broken pole9, at High Street, Church Street, Butts Road junction. Reported by Cllr Sunners | 14.11.18 | Reported to WCs |  |  |  | Chased by Clerk. Cllr Foley to chase 19.12.18. Cllr Mattock to chase 6.2.19

## Dec 2018
2018-12-01
H&S Impact H,M,L | Village Perception H,M,L | SBC division to deal |  | Request | Date issue received | CPC action | Date reported to Ward Cllrs | Ward Councillor/SBC action | Date Resolved | Other info
|  |  | 1 | Blocked drain on Castle View Road near CVPA | 15.12.18 | Reported to WCs | 15.12.18 | Reported to Highways |  | clearned
|  |  | 2 | Driveway access issue for Dykes Mews | 9.12.18 | Asked WCs to get SBC to look and will take photos of the situation | 17.12.18 | WCs asked Highways officers to check | 19.12.18 | Chased Jan 19
|  |  | 3 | Footpath sign torn from ground, near Unicorn Business park on Ridgeway Road | 17.12.18 | Reported to WCs. Not sure if SBC or Sustrans deal. | 17.12.18 | WC Mattock to ask if SBC deal
|  |  | 4 | Column 3 light at Turnball not working | 16.12.18 | Repoorted to WCs | 16.12.18 | Job reported to Street light team |  | Job 1014069 - new parts ordered for light
|  |  | 5 | Column 2 and 4 light on Turnball found to be broken | 16.12.18 | Direct report from SBC | 16.12.18 | Team to inspect & repair |  | Jobs 1014067 & 1014068
|  |  | 6 | Chased up dipped pavement at the Canney causing local flooding | 17.12.18 | Emailed WCs | 17.12.18 | WC Mattock to ask Highways to check | 4.1.19 | SBC are not going to fill this dip in the pavement

## Jan 2019
2019-01-01
H&S Impact H,M,L | Village Perception H,M,L | SBC division to deal |  | Request | Date issue received | CPC action | Date reported to Ward Cllrs | Ward Councillor/SBC action | Date Resolved | Other info
M | M | Highways | 1 | Pothole on High Street between Spar and New Road, can you report for patching please. | 3.1.19 | Reported to WCs | 3.1.19 | Brian to report to SBC |  | MHG004718 SBC shceduled work in to be done - date not known
H | M | streetsmart | 2 | Several blocked drains on High Street Strouds Hill | 3.1.19 | Reported to WCs | 3.1.19 | Brian to report to SBC |  | SBC reported back that they would not be clearing these drains. Clerk replies to BM stating this isnt a sufficient answer and we want him to challenge this for us.
M | M | Highways | 3 | Chased road repairs needed at junction of Orchard with Castle View Road - reported in Summer 2018 | 18.1.19 | Chased WCs | 18.1.19 | Fin to check with SBC | Fixed Feb 19 | Chased 31.1.19 as road surface breaking up. WC Mattock to chase.
H | M | Highways | 4 | Potentially dangerous parking at corner of Slipper Lane and Turnball - request Highways visit to assess | 9.1.19 | Reported to WCs | 9.1.19 | BM to report to SBC for advise |  | chased BM 23.1.19
|  |  | 5 | Pothole on A346 near roundabout and 40mph road signs not re-painted | 7.1.19 | Reported to WCs | 7.1.19 | FF to report to SBC |  | Signs on road re-painted Jan 19. BM chased potholes 1.2.19
|  |  | 6 | Requested red cones and signage be removed from A346 at roundabout | 31.1.19 | Reported to WC | 31.1.19 | FF to report to SBC |  | Belong to Highways England - clerk to report to them

## Feb 2019
2019-01-01
H&S Impact H,M,L | Village Perception H,M,L | SBC division to deal |  | Request | Date issue received | CPC action | Date reported to Ward Cllrs | Ward Councillor/SBC action | Date Resolved | Other info
L | L |  | 1 | Pothole on Turnball opposite Methodist church | 2019-02-11 | Reported to WCS | 2019-02-11 | WC Mattck reported on 13th
|  |  | 2 | The following street lights are in need of new lanterns: | 2019-02-13 | Reported to WCS | 2019-02-13 | WC Mattock reported to SBC 16th Feb
Turnball lamp post number 3
Castle View Road number 12
Castle View Road junction with Downs Road number 6
Junction Church Street/High Street/Butts Road number 10
Butts Road location on bend between lamp posts 9 and 10 light fixed to telegraph pole.
|  | Highways | 3 | Request for extra grit bin in Home Close | 11.2.19 | Reported to WCS | 11.2.19 | WC Mattock reported on 11th |  | reply from SBC: Good afternoon, I had a look at Home close today and noticed they already have a grit bin opposite number 53 so I don’t think we can justify putting another one there as most of the road is flat. The one that is there is empty at present but on the list to be filled. Regards
|  | Highways | 4 | Request for Ladymsith Road to be gritted in winter conditions | 11.2.19 | Reported to WCS | 11.2.19 | WC Mattock reported on 11th MHG005097 |  | Reply from SBC: Following snow, it is our normal practice that once the programmed routes are treated and have recovered to a good condition, if resources allow, we then treat hilly and exposed roads off the programmed routes.
Unfortunately, conditions were such that a number of major roads remained closed until late on Saturday with all our available resources concentrating on these and so we were not able to treat the hill routes over the weekend, with the exception of a very few roads that had been highlighted as priorities.
Come Monday, the thaw had begun and any treatments to the rapidly and naturally thawing roads would have been a costly and ineffective exercise, it was therefore decided to allow nature to take its course.
I can confirm that the grit bin has been added to the list to be filled as soon as possible.
H | M | Highways | 5 | Reported broken chevron sign on Hodson Road following RTA | 1.2.19 | Reported to WCs and already added and tagged on FB | 1.2.19 | WC Foley reported |  | Chased 11.2.19. Chased in EGPA meeting on 18.2.19
M | M |  | 6 | Uneven pavement between 22-28 Downs Road | 13.2.19 | Reported to WCs | 14.2.19 |  |  | Pavement is to be repaired - no date known.
|  | Highways | 7 | Pavement on A346 from plough down to last house no longer visible. Cllr Jefferies reported at EGPA feb meeting | 18.2.19 | Cllr Jefferies reported to W.cllr Mattock at EGPA feb meeting | 18.2.19
|  | Highways | 8 | 2 large curb stones at the M4 J15 junction on A346 have broken and moved way from the kerb. | 18.2.19 | Cllr Hill reported to Ward Cllr Mattock at EGPA Feb meeting | 18.2.19
|  | Highways | 9 | Large pothole on A346 going up the hill away from the M4 still needs fixing. | 18.2.19 | Cllr Hill reported again to WC Mattock at EGPA Feb meeting | 18.2.19
|  | Highways | 10 | Badbury bus stop down to the M4 there are load of abandoned road works signs still | 18.2.19 | As above | 18.2.19 | WC Mattock reported to SBC |  | SBC replied - these are Highways England signs - Clerk to report to H.E.
|  | Highways | 11 | New Road past Meadow stores towards pats roundabout - road sunk and broken up - chased up | 18.2.19 | Cllr Rawlings reported to WC Mattock at EGPA Feb meeting | 18.2.19
|  | Highways | 12 | Re-reported the patching on Hodson Road is breaking up again | 18.2.19 | Cllr Hill reported - as above | 18.2.19 |  |  | BM to talk to the Director of Highways to talk about the quality of patching work
|  |  | 13 | No street lights at Plough Hill - dangerous for pedestrians | 18.2.19 | Cllr Jefferies reported - as above | 18.2.19
|  |  | 14 | pothole at Ladysmith Road and Draycott Road junction | 14.2.19 | Clerk reported to WCS | 14.2.19 | WC Mattock reported to SBC on 16th
|  |  | 15 | Loose kerb stone on New Road near meadow stores | 24.2.19 | Reported to WCS | 27.2.19